## Slide 1: We will begin soon

## Slide 2: Presentation Panelists
Metro Purple Line Extension Team
Marlon Walker, Community Relations Manager
  Sections 1, 2 & 3 and Division 20
Ned Racine, Principal Community Relations Officer
  Section 1 and Division 20
Mindy Lake, Principal Community Relations Officer
  Section 1, Beverly Hills and Section 2
Glyssa Robles, Principal Community Relations Officer
  Section 3
Metro Business Interruption Team
Jessica Spearman, Principal Transportation Planner
Sidney Urmancheev, Transportation Associate
Metro New Media Team​
Stephanie Molen, Principal Community Relations Officer ​
Robyn Lopez, Community Relations Officer
Contractor Representatives and Presenters
Scott Donohue, STS Community Relations Coordinator
Yvette Ximenez, TPOG Project Information Coordinator
Joanna Amador-Dempsey, Modern Times Community Relations Director

## Slide 3
Metro D Line (Purple) Project
Today's Agenda
  Project Overview
  Division 20 Portal Widening and Turnback Facility
  Section 1 Construction Update
  Section 2 Construction Update
  Section 3 Construction Update
  Eat Shop Play
  7. Business Interruption Fund

## Slide 4
Purple Line Extension Alignment

## Slide 5
Sections 1, 2, & 3 Status
*Subject to change. The PLE project team is working to deliver the project consistent with Measure M.
 | Forecasted Schedule |  | 
Section | Section 1 | Section 2 | Section 3
Length | 3.92 Miles | 2.59 Miles | 2.56 Miles
New Stations | Wilshire/La Brea Wilshire/Fairfax Wilshire/La Cienega | Wilshire/Rodeo Century City/ Constellation | Westwood/UCLA Westwood/VA Hospital
Pre-Construction Activities | 2014 – 2015 | 2016 – 2018 | 2018 – 2019
Construction | 2015 – 2024 | 2018 – 2025 | 2019 – 2027
Operations | 2024 | 2025 | 2027

## Slide 6
Division 20 Portal Widening & Turnback Facility

## Slide 7
Project Overview
Arts District Project Area
  Operational improvements to Metro’s Division 20 Rail Yard will accommodate increased service levels on the Metro Red & Purple (B and D) Lines
  Improvements include:
  Widening of heavy rail portal
  Constructing new turnback facility
  Expanding and reconfiguring rail storage tracks
  Moving protected utilities
  Adding new power station
One Santa Fe
Tunnel Portal
Turnback Facility
Storage Tracks

## Slide 8
Current Work
National Cold Storage Facility
Strengthening Underneath the 1st Street Bridge
  Strengthening bridge enables removal of two supports (bents), allowing 12 tracks north of the bridge and 12 tracks south.
  Some nightwork will occur on weeknights from 9pm to 5am.
  Intermittent Saturday work may continue.
Rail strings on their way to the Western/Wilshire Station on a Friday night. Each rail string is 400-feet long and weighs 15,000 pounds.
Intense activity north of 1st Street Bridge includes portal widening. The buildings on the right will be demolished to allow room for more rail.

## Slide 10
Wilshire/La Brea Station Rendering

## Slide 11
Wilshire/La Brea Station Appendage Structures
*Dates subject to change.
Station Box
Appendage 1 *COMPLETE*
Appendage 3
Appendage 4
Appendage – Main Entrance
Appendages 6A and 6B
Appendage 5
Appendage 2
Appendage 1A
Phase 1.0
Phase 1.2
Phase 1.1
Phase 2.1
Phase 2.0
Station appendage locations
Schedule
  Phase 1.0
  *COMPLETE*
  Phase 1.2 – February through Sept 2021*
  Phase 1.1 – August through February 2022*
  Phase 2.0 – September 2021 through April 2022*
  Phase 2.1 – May 2022 through January 2023*

## Slide 12
Wilshire/La Brea Station
Working on the emergency exit stairs

## Slide 13: Wilshire/La Brea Station

## Slide 14
Pulling Rail to La Brea Station for Storage
Workers pause their pulling of permanent rail from the Wilshire/Western Station to the La Brea Station.
The rail is stored in the La Brea Station until the almost four miles of rail are installed in the tunnels.

## Slide 15
Wilshire/Fairfax Station Rendering

## Slide 16
Wilshire/Fairfax Station Appendage Structures
*Dates subject to change.
Station Box
Appendage – A1C *COMPLETE*
Appendage – A2B
Appendage – Main Entrance
Appendage – A2A
Appendages A1A and A1B
Phase 5.0
Phase 3.0
Phase 1.0
Phase 4.0
Phase 2.0
Schedule
  Phase 1.0 – April 2020 – October 2020
  *COMPLETE*
  Phase 2.0 – August 2020 – August 2021* (Extension Requested)
  Phase 3.0 – June 2020 – October 2021*
  Phase 4.0 – August 2021 – February 2022*
  Phase 5.0 – May 2021 - January 2022*
Station Box
Station appendage locations

## Slide 17
Wilshire/Fairfax Station
Working on the interior station walls

## Slide 18
Wilshire/La Cienega Station Rendering

## Slide 19
Wilshire/La Cienega Tunnel Boring Machine (TBM) Haul Out
Tunneling has been completed for the Purple Line Extension Section 1
Crews have been disassembling both machines so they can be transported out of the project area. The removal of the TBM components began in early July.
For approximately 12 weeks, crews will remove the TBM components piece by piece. The larger loads will be hauled out Sunday through Thursday, from 9pm to 6am. The smaller loads will be hauled out Monday through Saturday, from 7am to 4pm
City Traffic Control Officers will be onsite to assist traffic flow
Crane will conclude activities by 10pm
CHP will escort oversized loads
Location of TBM breakthrough

## Slide 20
Wilshire/La Cienega Station Appendage Structures
*Dates subject to change.
Appendages – Northeast
Appendage – South Gale
Appendage – Main Entrance
Appendages –
Southwest
Appendage – North Gale
Phase 1.1
Phase 2.2
Phase 1.1
Phase 1.2
Phase 2.1
Schedule*
  Phase 1.1 & 1.2: Q1 2021 to Q1 2022*
  Phase 2.1 & 2.2: Q2 2022 to Q4 2022
Station Box
Station appendage locations

## Slide 21
Wilshire/La Cienega Station Appendage Progress – Phase 1A

## Slide 22
Wilshire/La Cienega Station Appendage Progress – Phase 1A

## Slide 23: Replacement Parking
Locations for One Hour Free Parking:
  8447 Wilshire Bl: Accessible from N Hamilton
  8350 Wilshire Bl: Accessible from S Tower
  Please mention "Metro" upon entering the building to receive the 1st hour free

## Slide 24
Wilshire/La Cienega Construction Progress

## Slide 25
Wilshire/ La Cienega Construction Progress
Completed section of the station roof.

## Slide 27
Wilshire/Rodeo Station Rendering

## Slide 28
Wilshire/Rodeo Station Box
Rendering shows length of the underground station box on Wilshire Bl from Cañon Dr to Beverly Dr

## Slide 29
Wilshire/Rodeo Permitted Work Hours and Traffic Control
Work hours underneath the deck are 24 hours a day, 7 days a week. Deliveries of material, equipment, and concrete will be ongoing daily from Wilshire Bl. A breakdown of daily work hours on street level:
  From 7am to 9am and 4pm to 8:15pm, Wilshire Blvd. will remain open with three lanes in each direction between El Camino Dr. and Crescent Dr.
  From 9am to 4pm, Wilshire Blvd. may be reduced to two lanes in each direction between El Camino Dr. and Crescent Dr.
  From 8:15pm to 7am, Wilshire Blvd. may be reduced to one lane in each direction between El Camino Dr. and Crescent Dr.
Traffic control may also be implemented on Beverly Dr. At least one through traffic lane will be maintained in both directions.

## Slide 30: Wilshire/Rodeo Station Structure Construction through 2024

## Slide 31: Wilshire/Rodeo Installation of Station Invert Slab
Excavation within the station box and installation of most of the station invert were both completed in June.

## Slide 32: Wilshire/Rodeo Next Step: Exterior Walls
Progress of installing invert, conduits, rebar, piping, etc.

## Slide 33: Wilshire/Rodeo Wilshire Bl Current Condition

## Slide 34: Wilshire/Rodeo South Reeves Dr. Current Condition

## Slide 35
Wilshire/Rodeo Geotechnical Instrumentation
Where: Instruments will be installed within the tunnel alignment and station box area to monitor ground movement, settlement and other geological conditions
  Installations will be within the public right of way and within privately owned properties
Duration: Ongoing
Work Hours On Wilshire Bl:
  Weekdays, 7am to 4pm
Work Hours Off Wilshire Bl:
  Weekdays, 8am to 6pm
Example of 10-foot geotechnical instrumentation pole.

## Slide 36
Wilshire/Rodeo Request for Holiday Moratorium Exemption
An application has been sent to the City requesting a waiver of the Holiday Moratorium, which would allow work to continue after the Thanksgiving Holiday through New Year’s Eve.
  No work is planned for Thanksgiving Day, the day after Thanksgiving Day, Christmas Day or New Year’s Day.
If approved by City Council, the contractor will continue ongoing station and entrance construction, tunnel support, and installation and monitoring of geotechnical instrumentation.
This request will be brought forward for City Council consideration at a future meeting, meeting date to be determined.

## Slide 37: Wilshire/Rodeo: City of Beverly Hills Information
On Tuesday, Sept. 21, Beverly Hills City Council will consider a one-year extension of the North Cañon Dr closure
    Council will also consider Open Beverly Hills plan
    The two agenda items will be considered during the same meeting; however, each will be presented to Council separately because the items are not dependent on one another.
City Council initially approved the closure of North Cañon Dr and the wall installation in July 2018 for a minimum of two years up to six years. The wall was constructed in 2019.
Closure provides a safe and consistent traffic pattern for the businesses located on North Cañon Dr.
The 20-foot wall also mitigates construction noise and dust for the businesses on North Cañon.
If approved by City Council, the closure, sound-wall, and cul-de-sac will remain in place for another year to support station construction activities such as deliveries and concrete pours along Wilshire Blvd.

## Slide 38
Century City/Constellation Station Rendering

## Slide 39: Century City/Constellation Schedule

## Slide 40: Century City/Constellation Tunnel Boring Machine
A look inside a tunnel boring machine in Beverly Hills
A look inside station excavation in Century City

## Slide 41: Century City/Constellation Upcoming Sewer and Storm Drain Relocation
Anticipated Start Date:
  August/September 2021
Anticipated Traffic Control*:
  Lane closures on Avenue of the Stars
  Night closures (8pm to 6am) will be required in early stages
*pending city approval

## Slide 42: Century City/Constellation Senator Padilla Infrastructure Tour

## Slide 43: Century City/Constellation Excavation Opening Photo

## Slide 44: Century City/ Constellation Excavation Opening

## Slide 45: Century City/Constellation Ruth and Harriet Tunnel Boring Progress Map
Tunneling Statistics (7/30/2021) | 
Ruth | 11,510 feet (total journey) 19% complete
Harriet | 16,510 feet (total journey) 20% complete
> Tunneling Duration:
Approximately 2 years

## Slide 47
Section 3 Tunnel From Century City to Westwood

## Slide 48
Westwood/UCLA Station Rendering (Northwest Entrance)

## Slide 49
Westwood/UCLA Station Rendering (Northeast Entrance)

## Slide 50
Westwood/UCLA Station Rendering (Southeast Entrance)
DRAFT

## Slide 51
Westwood/UCLA Station Box
Rendering shows length of the underground station box on Wilshire Bl between Westwood Bl and Veteran Av

## Slide 52
Westwood/UCLA Sanitary Sewer and Storm Drain Relocation
Utility work will be done in stages
Wilshire Blvd and Gayley Ave.
Work Hours: Friday, 11pm through Monday, 6am;
9am to 3:30pm and 9pm to 6am.
Traffic Control:
Wilshire Bl will always have one lane open in each direction.
Building access will be maintained.

## Slide 53
Westwood/UCLA Traffic Signal Conduit Relocation
Utility work will be done in stages
Wilshire Blvd, Gayley Ave, Kinross Ave.
When: July 26 – August 13, Monday to Friday, 9pm to 6am
Traffic Control:
•Intermittent sidewalk closures.
•Lane reductions.
•Building access will be maintained.
Kinross Ave
Gayley Ave

## Slide 54
Piling for the Westwood/UCLA Station
Piles support the walls underground for the Westwood/UCLA Station and support the decking that will be built over the street.
Pile installation will be on Wilshire Bl between Westwood Bl and Veteran Av.
Pile installation includes:
Drilling holes on average 85 ft in depth, place piles, back fill piles with concrete
Complete and repeat around the perimeter of the station box
Approximately 449 piles for the Westwood/UCLA Station, every 7 feet
All work occurs behind K-rail

## Slide 55
Piling for the Westwood/UCLA Station
Schedule
• Start in mid-August 2021* on north side of Wilshire Bl.
• There are 20 stages of pile installation with varying traffic patterns
•Approximately 9 months duration*
Typical Work Schedule:
• K-rail traffic configuration remains in place for entire duration of piling
Work occurs 7 days a week behind k-rail
Additional lane reductions may occur during off-peak hours
Work Activities:
• 7am to 9pm, drilling
• 9pm to 11pm, non-drilling (equipment maintenance, cleaning, set up)
*Construction is dynamic and the schedule is subject to change​

## Slide 56
Piling for the Westwood/UCLA Station

## Slide 57
Piling for the Westwood/UCLA Station

## Slide 58
Piling for the Westwood/UCLA Station in Lot 36
Anticipated Start: August 23, 2021

## Slide 59
Westwood/UCLA North Side Piling (Stage 1): Estimated 7 months
Anticipated Start: September 2021
24/7

## Slide 60
Westwood/UCLA North Side wall Piling (Stage 1F + 1): Estimated 4 weeks
Nightly:
Mon–Thurs 9pm to 6am
Weekend:
9pm Fri – 6am Mon

## Slide 61
Westwood/UCLA Temporary Bus Stops Relocation

## Slide 62
Westwood/VA Hospital Station Rendering

## Slide 63
Westwood/VA Hospital Station Rendering (Bonsall Av)

## Slide 64
Westwood/VA Hospital Station Box

## Slide 65
Westwood/VA Hospital Station Passenger Pick-Up/Drop-off Zone
Short term passenger drop-off and pick up zone (15-30 minutes max)
Designed to minimize traffic congestion while maintaining pedestrian and commuter access

## Slide 66
Westwood/VA Hospital Station Construction Progress

## Slide 67
Westwood/VA Hospital Station Construction Progress

## Slide 68
Westwood/VA Hospital 405 Ramps Closure for Piling
Date: October 2021
Hours: 9pm Friday through 5am Monday

## Slide 69
Westwood/VA Hospital Upcoming Waterline Work
Wilshire Blvd
Federal Ave
Traffic Control:
VA Hospital access will be detoured nightly along Sepulveda Bl and Santa Monica Bl to Sawtelle Bl and Dowlen Dr.
Where: Wilshire Bl, Federal Av, and Bonsall Av
When: 2022
Work Hours: Vary depending on the work scheduled in each stage.
Monday to Friday 9am to 3pm, 7pm to 6am and Saturday to Sunday 8am to 5pm

## Slide 70
Stay in touch
Boss Sushi
270 S. La Cienega Bl
Japanese Sushi restaurant in Beverly Hills
Business hours Mon - Sat : 5pm -10pm Sun : 5pm- 9pm
bosssushi.com

## Slide 71
Stay in touch
Social media post on Twitter & Facebook
Spotlighting re-opened businesses
Holidays, promotions, and events

## Slide 72
Stay in touch
Print ads on local publications

## Slide 73
Stay in touch
Contact Us
> For more information on Eat Shop Play visit​
metro.net/eatshopplay ​
> Send an email to eatshopplay@metro.net

## Slide 74
Business Interruption Fund (BIF)

## Slide 75: Metro’s Business Interruption Fund
BIF Information and Eligibility
Financial assistance to small “mom & pop” businesses with 25 or fewer full-time employees directly impacted by Metro Rail construction along three project areas​:
  Crenshaw/LAX Transit Project​
  Purple Line Extension, Sections 1, 2 & 3​
  Regional Connector Project, Little Tokyo area & 2nd/Broadway Segment*
Businesses must be located immediately adjacent to the rail corridor and meet other eligibility requirements​
Grant amounts are determined by business revenue loss directly related to period of Metro construction disruption​
Businesses may receive up to $50,000 per impact year
*Segment eligibility based on full street closure with duration greater than six continuous months. Eligibility ended 6/30/17.​

## Slide 76
Metro’s Business Interruption Fund
Metro’s Business Interruption Fund (BIF) is accepting applications for transit rail construction impact along the Crenshaw/LAX Transit Project, the Little Tokyo area of the Regional Connector and Sections 1, 2 and 3 of the Purple Line Extension sustained from March 20, 2020, forward (during the COVID-19 pandemic).
Small “mom and pop” businesses that experienced transit rail construction impact during the COVID-19 pandemic may be eligible.
Potentially eligible small business owners may contact BIF Fund Administrator Pacific Coast Regional at 213.739.2999 x223 or Metro at bif@metro.net.
Metro does not cover revenue loss nor fixed operating expenses related to COVID-19 impacts.

## Slide 77
Metro’s BIF during COVID-19 Pandemic
Chart: 
| Crenshaw/LAX Transit Project | Purple Line Extension Section 1 | Purple Line Extension Section 2 | Regional Connector, Little Tokyo Area | Regional Connector, 2nd/Broadway Segment
Total Grant Amount | 15090988.93 | 5485204.34 | 2111053.94 | 1996164.16 | 950164.03
  *BIF Grants do not cover COVID-19 related impacts.
Value of BIF Grants Awarded:
$31,858,285.76*

## Slide 78
Stay in Touch
Lunch with Us Webinar: Monthly Construction Update Beverly Hills Section 1 & 2 September 1, 2021, 12noon
Link to webinars available at metro.net/purple
213.922.6934
purplelineext@metro.net
metro.net/purple
@purplelineext
facebook.com/purplelineext