## Slide 1: Thank you for joining us!

## Slide 2: Agency Updates
https://www.taptogo.net/LIFE_Application

## Slide 3: Program Update
Metro Art Program Update
By Clare Haggarty, Senior Manager, Public Art & Exhibition Programs
Notes: Hi this is Clare Haggarty, Senior Manager with Metro Arts + Community Enrichment, I am excited to announce the artists recently commissioned for the stations for sections 2 and 3 of the D Line extension, joining the artists already working on section 1!

## Slide 4: Section 1 Artist Review Panel
Gretchen Baker/Brian Bergeron, Natural History Museum of Los Angeles County
Doris Berger, Academy Museum of Motion Picture Arts and Sciences
Heeseon Choi, Korean Cultural Center
Harry Gamboa Jr., Artist
Rita Gonzalez, Los Angeles County Museum of Art
Suzanne Isken, Craft Contemporary
Naima J. Keith, California African American Museum/Los Angeles County Museum of Art
Stephanie Vahn, Beverly Hills Arts and Culture Commission
Notes: For a little background - this slide lists the distinguished panel of arts professionals representing the project area, who evaluated and made the recommendations for the Section 1 artists, who were commissioned in 2018.

## Slide 5
Section 1 Commission Artists
Mariana Castillo Deball (Wilshire/La Cienega)
Mark Dean Veca (Wilshire/La Brea)
Ken Gonzales-Day (Wilshire/Fairfax)
Todd Gray (Wilshire/La Cienega)
Karl Haendel (Wilshire/Fairfax)
Soo Kim (Wilshire/La Cienega)
Eamon Ore-Giron (Wilshire/La Brea)
Fran Siegel (Wilshire/La Brea)
Susan Silton (Wilshire/Fairfax)
Notes: These artists are hard at work in the artwork design phase right now. I imagine you might recognize a lot of the artists as they are known around the world, although many are from right here in LA County.

## Slide 6: Sections 2 + 3 Artist Review Panel
Michael Amescua, Artist and Veteran
LeRonn P. Brooks, The Getty Research Institute
Connie Butler, The Hammer Museum at UCLA
Ken Gonzales-Day, Artist
Arthur Lewis, United Talent Agency Artist Space
Thao Nguyen, Creative Artists Agency
Anna Sew Hoy, UCLA School of the Arts and Architecture
Jean Tardy-Vallernaud, Century City Arts Council
Cate Thurston, The Skirball Cultural Center
Stephanie Vahn, Beverly Hills Arts and Culture Commission
Notes: And most recently Metro again convened an esteemed panel of internationally recognized art experts representing Beverly Hills, Century City, and Westwood, as well as representing the student population, veterans and other future riders. Artists were evaluated and short-listed from Metro’s current Artist Pool. Over 1,500 artists applied to the Artist Pool, the panel considered artists from across the nation and their recommendation represents artists of the highest caliber for all of these stations.

## Slide 7: Section 2 Commissioned Artists
Eddie Rodolfo Aparicio (Century City/Constellation Station) Sarah Cain (Century City/Constellation Station) Phung Huynh (Century City/Constellation Station) Oscar Magallanes (Century City/Constellation Station) Meleko Mokgosi (Wilshire/Rodeo Station) Rigo 23 (Wilshire/Rodeo Station) Analia Saban (Century City/Constellation Station) Devon Tsuno (Wilshire/Rodeo Station)
Notes: Here are the artists recently commissioned for section 2 which includes the Wilshire/Rodeo and Century City/Constellation Stations.

## Slide 8
Notes: And here they are – and they are all getting started on their artworks as we speak.

## Slide 9: Section 3 Commissioned Artists
Moses X. Ball (Westwood/UCLA Station) Sandow Birk (Westwood/VA Hospital Station) Victoria Fu + Matt Rich (Westwood/VA Hospital Station) Karen Hampton (Westwood/UCLA Station) Yunhee Min (Westwood/UCLA Station) Gala Porras-Kim (Westwood/UCLA Station) Francesco Simeti (Westwood/VA Hospital Station) Eloy Torrez (Westwood/VA Hospital Station) Iris Yirei Hu (Westwood/UCLA Station)
Notes: And these are the artists commissioned for section 3 which includes the Westwood/UCLA and Westwood/VA Hospital Stations.

## Slide 10
Notes: And here they are as well. The artists for sections 1, 2 and 3 bring incredible experience and artistic excellence to the creative process, as well as a sensitivity to the site specificity of these art commissions and their relationships to the neighborhoods and people served.

## Slide 11: More Metro Art!
Subscribe for Email Updates:
metro.net/art
Follow us on:
Facebook: Metro Art Los Angeles ​
Instagram: @metro.art.la
Notes: Stay tuned for exciting Meet the Artist events where you can get a sneak peek into the artists’ practice and design process for these commissions. Subscribe to email updates and follow Metro Art on Instagram and Facebook! A number of the artists are represented by galleries here in Los Angeles County and at least one has a solo show right now, Sandow Birk, at Track 16 Gallery so keep these artists on your radar!

## Slide 12: Presentation Panelists
Metro Purple Line Extension Team
Kasey Shuda, Community Relations Director - Interim
  Sections 1, 2 & 3 and Division 20
Marlon Walker, Community Relations Manager
  Sections 1, 2 & 3 and Division 20
Ned Racine, Principal Community Relations Officer
  Section 1 and Division 20
  Mindy Lake, Principal Community Relations Officer
  Section 1, Beverly Hills and Section 2
  Glyssa Robles, Principal Community Relations Officer
  Section 3
Metro New Media Team​
Ginny Brideau, Manager, Community Relations New Media Team
Stephanie Molen, Principal Community Relations Officer New Media Team
Jesus Galeno, Community Relations New Media Team
Metro Arts + Community Enrichment
Clare Haggarty, Senior Manager, Public Art & Exhibition Programs
Contractor Representatives and Presenters
Scott Donohue, STS Community Relations Coordinator
Matt Evans, TPOG Project Information Coordinator
Metro Business Interruption Fund Team
Jessica Spearman, Principal Transportation Planner
Eric Chun, Sr. Transportation Planner (Interim)

## Slide 13: Today's Agenda
  Project Overview
  Division 20 Section 1 Construction Update Section 2 Construction Update Section 3 Construction Update
  Eat Shop Play
  Business Interruption Fund

## Slide 14
Purple Line Extension Alignment

## Slide 15
Sections 1, 2, & 3 Status
*Subject to change. The PLE project team is working to deliver the project consistent with Measure M.
 | Forecasted Schedule |  | 
Section | Section 1 | Section 2 | Section 3
Length | 3.92 Miles | 2.59 Miles | 2.56 Miles
New Stations | Wilshire/La Brea Wilshire/Fairfax Wilshire/La Cienega | Wilshire/Rodeo Century City/ Constellation | Westwood/UCLA Westwood/VA Hospital
Pre-Construction Activities | 2014 – 2015 | 2016 – 2018 | 2018 – 2019
Construction | 2015 – 2024 | 2018 – 2025 | 2019 – 2027
Operations | 2024 | 2025 | 2027

## Slide 17: Project Overview
  Operational improvements to Metro’s Division 20 Rail Yard will accommodate increased service levels on the Metro Red and Purple (B and D) Lines
  Improvements include:
    Widening of heavy rail portal
    New turnback facility
    Expansion and reconfiguration of rail storage tracks
Benefits
  Faster and more frequent service
Arts District Project Area
One Santa Fe
Tunnel Portal
Turnback Facility
Storage Tracks

## Slide 18: Current work- Portal Area
Before Construction
Bing Image
Current area*
*Delineations on the image are not to scale.

## Slide 20: Wilshire/La Brea Station Rendering

## Slide 21
Wilshire/La Brea Station Box
Outline of the Wilshire/La Brea underground station box on Wilshire Bl. from Orange Dr. to Detroit St.

## Slide 22: Wilshire/La Brea Station: Phase 1 Restoration (April 22 to July 11, 2022)
Restoration work to progress from East to West
Weekend 1: April 22 – 25
Weekend 2: April 29 – May 2
Weekend 3: May 6 – 9
Weekend 4: May 13 – 16
Weekend 5: May 20 – 23
Memorial Day (No Work): May 27 – 30
Weekend 6: June 3 – 6
Weekend 7: June 10 – 13
Weekend 8: June 17 – 20
Weekend 9: June 24 – 27
Fourth of July (No Work): July 1 – 4
Weekend 10: July 8 – 11

## Slide 23: Decking Restoration – Weekend 1

## Slide 24: Wilshire/La Brea Station: Traffic Detour Routes

## Slide 25: Wilshire/La Brea Station: Post Decking Restoration
Curb, Gutter, Bus Pad Restoration
Following deck removal between Orange Dr. and La Brea Ave., a work zone will be established on the north side of Wilshire Blvd. between Mansfield Ave. and La Brea Ave.
This work zone will support curb and gutter restoration and the installation of streetlights, tree wells, wheelchair ramps, and bus lanes.
Starting: July 2022*
Duration: 3 – 6 months*
*Dates Subject to Change
Sycamore Restoration
Orange Restoration
A traffic control plan for this phase of street restoration is being developed. More specific information will be available later this year.

## Slide 26: Wilshire/Fairfax Station Rendering

## Slide 27
Wilshire/Fairfax Station: Appendage Structures
*Dates subject to change.
Station Box
Appendage – A1C *COMPLETE*
Appendage – A2B
Appendage – Main Entrance
Appendage – A2A
Appendages A1A and A1B
Phase 5.0
Phase 3.0
Phase 1.0
Phase 4.0
Phase 2.0
Schedule
  Phase 1.0 – April 2020 – October 2020
  *COMPLETE*
  Phase 2.0 – August 2020 – July 2022*
  Phase 3.0 – June 2020 – July 2022*
  Phase 4.0 *COMPLETE*
  Phase 5.0 – *COMPLETE*
Station Box
Station appendage locations

## Slide 28
Wilshire/Fairfax Station

## Slide 29
Wilshire/La Cienega Station Rendering

## Slide 30
City of Los Angeles Work
Eastbound Directional Closures at Wilshire Bl & San Vicente Bl
This traffic control will support ongoing station and appendage construction at the Fairfax Station.
Beginning in May 2022, STS may begin implementing weekend eastbound directional closures on Wilshire Bl at the San Vicente Bl intersection. Eastbound Wilshire Bl between Tower Dr and San Vicente Bl will be reduced to a single lane. Through movements at San Vicente Bl will be restricted. Turn movements will be maintained onto San Vicente Bl.
The proposed work hours are Friday at 9pm through Monday at 6am*
There will be a signed detour that begins within the City of Beverly Hills
*Subject to Approval

## Slide 31
Wilshire/La Cienega Station Appendage Work
Why: Multiple appendages will be required for each station on the Purple Line Extension
Each appendage structure houses a vital function for the stations:
  Emergency exits
  Utility rooms
  Ventilation rooms
  Entrance and exit structures
When: Began in March 2021 through 2023*
Where: Information about specific traffic control and work hours will be available in future community meetings and construction notices
Coordination with impacted businesses will be conducted prior to the start of the next phase of appendage work

## Slide 32
Wilshire/La Cienega Station: Appendage Structures Phase 1A
Appendages – Northeast
Appendage – Main Entrance
Phase 1A
Phase 1A
Station Box
Station appendage locations

## Slide 33
Wilshire/La Cienega Station Appendage Work
*Dates subject to change.
Phase 1A Traffic Control (March 2021 through November 2022)*
Wilshire Blvd. between San Vicente Blvd. and La Cienega Blvd. reduced to two lanes in each direction.
Left turns from Wilshire Blvd. onto Gale Dr. will be restricted from both directions. Left turns from Tower Dr. onto westbound Wilshire Blvd. will be restricted.
The east/ west crosswalks at Gale will be maintained.
The north sidewalk between San Vicente Blvd. and Gale Dr. will be closed during this phase of work. A pedestrian detour for east/west travel will be in place on the south side of Wilshire. Access to 8383 Wilshire will be maintained.
The loading zone in front of the Saban Theatre on Wilshire Blvd will be closed over the duration of this closure.
A full closure of Gale Dr. north of Wilshire Blvd. will be in place during Phase 1B of this work.

## Slide 34
Wilshire/La Cienega Station: Appendage Structures Phase 1B
*Dates subject to change.
Phase 1B
Phase 1B Traffic Control (January 7, 2022 through mid-May 2022)*
Wilshire Blvd. between San Vicente Blvd. and La Cienega Blvd. reduced to two lanes in each direction
Gale Dr. north of Wilshire Blvd. will be fully closed for approximately 4 months*
Left turns from Wilshire Blvd. onto Gale Dr. will be restricted.
Left turns from Tower Dr. onto Wilshire Blvd. will be restricted.
The north/south crosswalks at Gale Dr will be closed
The north sidewalk between San Vicente Blvd. and west of Gale Dr. will be closed during this phase of work. A pedestrian detour for east/west travel will be in place on the south side of Wilshire. Access to 8383 Wilshire will be maintained.
The loading zone in front of the Saban Theatre will be closed over the duration of this closure.
Station Box
Station appendage locations

## Slide 35
Wilshire/La Cienega Station Appendage Structures – 1C
*Dates subject to change.
Appendages – Northeast
Phase 1C
Phase 1C Traffic Control (mid-May 2022 through November 2022)*
  Wilshire Blvd. between San Vicente Blvd. and La Cienega Blvd. reduced to two lanes in each direction
  Southbound Gale Dr. from north of Wilshire Blvd. to Wilshire Blvd. will be closed to through traffic for approximately 7 months.* Northbound traffic on Gale Dr. will be intermittently maintained.
  Left turns from Wilshire Blvd. onto Gale Dr. will be restricted.
  Left turns from Tower Dr. onto Wilshire Blvd. will be restricted.
  The north/south crosswalk on the east side of Gale will be maintained. The west side crosswalk will be closed
  The north sidewalk between San Vicente Blvd. and west of Gale Dr. will be closed during this phase of work. A pedestrian detour for east/west travel will be in place on the south side of Wilshire. Access to 8383 Wilshire will be maintained.
  The loading zone in front of the Saban Theatre will be closed over the duration of this closure.
Station Box
Station Box
Station Box

## Slide 36
Wilshire/La Cienega Station Appendage Progress – Phase 1A

## Slide 37: Replacement Parking
Locations for One Hour Free Parking:
  8447 Wilshire Bl: Accessible from N Hamilton
  8350 Wilshire Bl: Accessible from S Tower
  Please mention "Metro" upon entering the building to receive the 1st hour free

## Slide 38
Concrete and Material Deliveries
Where: Structural work on the station underneath Wilshire Bl is generally conducted from the Gale Yard and from Wilshire Bl
Work Hours: 7am to 4pm during bump out implementation
Traffic Controls*:
  Westbound Wilshire Bl will be intermittently reduced to one lane between San Vicente Bl and Hamilton Dr
  Daily closures will be utilized in support of ongoing work activities in the staging yard at Gale Dr
Deck Panel Access – Hamilton Dr (9am to 4pm, weekdays; 7am to 6pm, Saturdays)
  Beginning in April, intermittent deck panel access may be implemented within the Wilshire/Hamilton intersection.
  Wilshire will be reduced to a single lane in each direction between Tower Dr and Stanley Dr
  Left turns from Wilshire to Hamilton will be restricted. Through traffic on Hamilton will be restricted at Wilshire.
Outside Gale Staging Yard
Noise Mitigations: will remain in place
  Sound blankets around noisy equipment
  Trucks equipped with low-impact backup alarms
  Nylon straps used to lift material

## Slide 39
Next Steps: Station Construction
Construction of station roof will continue through 2022
Each roof placement will be 60 feet by 60 feet
Work activities in support of concrete and deliveries will be conducted within the staging yards, and occasionally on Wilshire Bl
Daily construction activities may be conducted underneath Wilshire Bl and from both Staging Yards for 24 hours a day
Illustration of station interior design

## Slide 40: La Cienega Station Progress
Looking East
Looking West

## Slide 41
Instrumentation Work
When: Ongoing in 2022
Traffic Controls:
  Intermittent lane reductions on Wilshire Bl, La Cienega Bl, and side streets during off-peak hours may be in place to support the maintenance of geotechnical instruments in the Wilshire Bl and La Cienega Bl area
  Intermittent lane reductions may be in place on Wilshire Bl, west of La Cienega Bl, to support coring survey work under Wilshire Bl
Additional details on this work will be available in future construction notices
Example of instrumentation drilling

## Slide 43
Wilshire/Rodeo Station Rendering

## Slide 44
Wilshire/Rodeo Station Box
Rendering shows length of the underground station box on Wilshire Bl from Cañon Dr to Beverly Dr

## Slide 45
Wilshire/Rodeo Station: Permitted Work Hours and Traffic Control
Work hours underneath the deck are 24 hours a day, 7 days a week. Deliveries of material, equipment, and concrete will be ongoing daily from Wilshire Bl. A breakdown of daily work hours on street level:
  From 7am to 9am and 4pm to 8:15pm, Wilshire Blvd. will remain open with three lanes in each direction between El Camino Dr. and Crescent Dr.
  From 9am to 4pm, Wilshire Blvd. may be reduced to two lanes in each direction between El Camino Dr. and Crescent Dr.
  From 8:15pm to 7am, Wilshire Blvd. may be reduced to one lane in each direction between El Camino Dr. and Crescent Dr.
Traffic control may also be implemented on Beverly Dr. At least one through traffic lane will be maintained in both directions between 9am-4pm and 8pm-7am.
From 9am to 4pm, S. Reeves Dr. may be reduced to one lane northbound to accommodate delivery of material and equipment. A flagger will be on site to assist motorists with 2-way traffic.

## Slide 46: Wilshire/Rodeo Station: Structure Construction through 2024

## Slide 47
Wilshire/Rodeo Progress: Installing invert, conduits, rebar, piping

## Slide 48: Wilshire/Rodeo Exterior Walls Progress

## Slide 49: Wilshire/Rodeo Exterior Walls Progress

## Slide 50: Wilshire/Rodeo Tunneling Progress

## Slide 51: Wilshire/Rodeo Station: Construction Progress
Entrance invert rebar installation progress.

## Slide 52
Upcoming SCE Installation Work
Where: Wilshire Blvd. between Dayton Way and Rexford Dr.
Duration: ~ 7 months [Anticipated start in June]
Work Hours: Weekdays, 9am to 4pm and 8pm-7am
Traffic Control:
  Wilshire Blvd. may be reduced to two lanes in each direction during the day and one lane overnight
Contractor will begin installation of SCE Permanent Power Feeds to the station.
*Pending approval from City Of Beverly Hills

## Slide 53
Upcoming Ground Improvement/Cross Passage Work
The contractor will begin ground improvement work along the tunnel alignment in preparation for the construction of cross passage tunnels.
When: Anticipated to begin in late May [~ Mon. 5/23]
  (Locations near High School to begin after break)
Where: *14 locations; First 7 work sites noted on map
Work Hours: Monday-Friday 8am-6pm; closures remain in place 24/7 until each location is completed
Duration: 2-4 weeks/location
*Additional notices detailing dates & closure information will be provided in advance

## Slide 54
Wilshire/Rodeo Station: Geotechnical Instrumentation
Where: Instruments will be installed within the tunnel alignment and station box area to monitor ground movement, settlement and other geological conditions
  Installations will be within the public right of way and within privately owned properties
Duration: Ongoing
Work Hours On Wilshire Bl:
  Weekdays, 7am to 4pm and 8pm to 7am
Work Hours Off Wilshire Bl:
  Weekdays, 8am to 6pm and 8pm to 7am
Example of 10-foot geotechnical instrumentation pole.

## Slide 55: Tunnel Boring Machine (TBM) Update
Tunneling Statistics As of (5/11/2022) | 
Ruth | 11,510 feet (total journey) 60% complete
Harriet | 11,510 feet (total journey) 65% complete
Both TBM’s have passed through the Wilshire/Rodeo Station
Will continue mining east towards Wilshire/La Cienega
Tunneling Duration: Approximately 2 years from the start
Remaining Duration: 4-6 months

## Slide 56: Century City/Constellation Station Rendering

## Slide 57: Century City/Constellation: Station Box
Length of the underground station box on Constellation Blvd.
from Century Park East to Avenue of the Stars.

## Slide 58: Century City/Constellation: Station Excavation
Excavation of the underground station underneath Constellation Blvd. is in progress and will continue until reaching approximately 100 feet in depth.
Work Hours: 24 hours a day, 5 days a week (Monday – Friday)
Anticipated Completion: 1st quarter 2023
Temporary partial traffic lane closures may be required on Constellation Blvd. both east and west of Avenue of the Stars to facilitate this work.

## Slide 59: Station Entrance Excavation

## Slide 60: Stage 7B (Steady State Closure)
Anticipated Duration:
  2 years
Traffic Control:
  One eastbound and westbound lane are accessible from CPW to AOS
  Maintaining access to Westfield driveways and Fairmont Century Plaza Hotel
Driveway open
Driveway open
Driveway open
Delivery driveway open

## Slide 61: Sanitary Sewer and Storm Drain Relocation
Ongoing: (Work started in March 2022)
Anticipated Duration: Through mid-2022
Anticipated Traffic Control:
  Lane closures on Avenue of the Stars
  Night closures (8pm to 6am) will be required in early stages
Notes: Relocation was originally meant to be done in several subsequent stages of work. However, we were able to combine some stages of work to expedite the relocation work in general.

## Slide 62: Stage 7B-1 (Nighttime Closure)
Anticipated Duration: Through 5/13
Work Hours: Night; 8pm to 6am
What to Expect: Potholing, piling, shoring, and utility installation
Driveway open
Driveway open
Driveway open
Delivery driveway open
Work Area
Work Area
Traffic Control:
  SB AOS reduced to one lane north of Constellation Bl
  No right turns on SB AOS onto WB Constellation Bl
  Intermittent closure of access lane on south side of Constellation Bl
Intermittent closure

## Slide 63: Stage 7B-2 (Nighttime Closure)
Anticipated Duration: Through 5/13
Work Hours: Night; 8pm to 6am
What to Expect: Potholing, piling, shoring, and utility installation
Driveway open
Driveway open
Driveway open
Delivery driveway open
Work Area
Work Area
Work Area
Work Area
Traffic Control:
  NB AOS reduced to one lane north of Constellation Bl
  Intermittent closure of access lane on south side of Constellation Bl
Intermittent closure
Notes: Closing right turn on NB AOS to EB Constellation or just go around closure?

## Slide 64: Stage 7B-5 (Nighttime Closure)
Anticipated Duration: Through 5/13
Work Hours: Night; 8pm to 6am
What to Expect: Excavation, shoring, and utility relocation
Traffic Control:
  No left turns on NB AOS onto WB Constellation Bl
  Intermittent closure of access lane on south side of Constellation Bl
Driveway open
Driveway open
Driveway open
Delivery driveway open
Intermittent closure
Notes: Closing right turn on NB AOS to EB Constellation or just go around closure?

## Slide 65: Stage 8
Anticipated Duration: ~ 4 months
Implementation will require full closure of AOS (Santa Monica to Olympic) on Friday night (anticipated for Friday, 5/13.)
Work Hours: 24 hours a day, 7 days a week
What to Expect: Potholing, piling, shoring, and utility installation
Work Area
Work Area
Driveway open
Driveway open
Driveway open
Delivery driveway open
*pending approval from City of Los Angeles
Intermittent closure
Traffic Control:
  No left turns on NB AOS onto WB Constellation Bl
  Intermittent closure of access lane on south side of Constellation Bl.

## Slide 66: Stage 8.1
Anticipated Duration: Intermittently during Stage 8
Implementation Schedule: 5/14 – 7am to 7pm
5/15 – 7am to 7pm
Work Hours: 8pm to 6am; Intermittently after 5/15
What to Expect: Potholing, piling, shoring, and utility installation
Driveway open
Driveway open
Driveway open
Delivery driveway open
Intermittent closure
Traffic Control:
  No left turns on SB AOS onto EB Constellation Bl | Left turn restricted on SB AOS at Constellation Bl.
  Intermittent closure of access lane on south side of Constellation Bl.
  Implementation of this closure on Sat, 5/14 & Sun, 5/15 following implementation to complete piling at intersection
*pending approval from City of Los Angeles
Night-time additional closure

## Slide 68
Section 3 Tunnel From Century City to Westwood

## Slide 69
Section 3 Tunneling Progress
Tunneling Statistics as of 5/2/2022
Iris (TBM 1)
Aura (TBM 2)
5,929 feet
43% complete
4,864 feet
35% complete
Future Station Boxes

## Slide 70
Westwood/UCLA Station Rendering (Northwest Entrance)

## Slide 71
Westwood/UCLA Station Rendering (Northeast Entrance)

## Slide 72: Westwood/UCLA Station Rendering (Southeast Entrance)
DRAFT

## Slide 73
Westwood/UCLA Station Box
Rendering shows length of the underground station box on Wilshire Bl between Westwood Bl and Veteran Av

## Slide 74: Westwood/UCLA Station Piling
314 Piles Installed. 468 Total Piles for Station.

## Slide 75
Piling Progress Westwood/UCLA Station

## Slide 76: Westwood/UCLA Piling Stage 2: June 2022 (End of June)
Nightly:
Mon–Thurs, 9pm to 6am
Weekend:
Continuous 9pm, Fri to 6am, Mon
*Construction is dynamic and subject to change​.
Sidewall closed

## Slide 77: Westwood/UCLA Piling Stage 2F- May 20, 2022
Nightly:
Mon- Fri, 9pm to 6am
Weekends:
Continuous, 9pm, Fri to 6am, Mon
*Construction is dynamic and subject to change​.​

## Slide 78: Decking
Decking is a process where the street is excavated from curb to curb at a depth of about 10 to 12 feet. The deck beams are installed over the piles that have been installed. The concrete precast panels are place over the piles and create a temporary street surface. The panels get restriped for vehicular and pedestrian use.
Temporary partial street closures will be implemented on Wilshire Bl. Traffic will be detoured around the construction work.
Decking is expected to begin in Summer 2022.

## Slide 79: Decking Traffic Control – Stage 1
The plans are being finalized for approval by all the agencies.
Eastbound Wilshire Bl traffic access maintained.
Westbound traffic detoured at Westwood either to Kinross Av or Ohio Av.
*Traffic control plans pending approval

## Slide 80: Example of Decking on Bonsall Av.

## Slide 81
Dewatering Wells on Wilshire Bl
The dewatering wells on Wilshire Bl will be used to maintain and clean the tunnel boring machines (TBMs) underground.
  Work will be done in stages.
  Noisy work will be done during the day.
  Utility service will not be interrupted.
  Access to driveways will be maintained.

## Slide 82: Drilling on Wilshire Bl near Malcolm Av.
May 6, 9pm through May 7, 6pm – Restriping and barrier setup.
May 9 to 20, 9am to 3:30pm- Drilling, installing wells, piping, and manholes.
Access to driveways will be maintained.
Left turns may be restricted.

## Slide 83: Sewer Lateral on Wilshire Bl near Malcolm Av
Access to driveways will be maintained.
Left turns may be restricted.
May 21, 9am to 3:30pm- Sewer lateral
Utility service will not be interrupted.

## Slide 84
Generator in Center Median of Wilshire Bl
May 23, 24/7 for approximately 2 months – Generator in Median.
Wilshire Bl will have 3 lanes open in each direction.
Access to driveways will be maintained.
Left turns may be restricted.

## Slide 85: Westwood/VA Hospital Station Rendering

## Slide 86
Westwood/VA Hospital Station Rendering (Bonsall Av)

## Slide 87
Westwood/VA Hospital Station Box

## Slide 88: VA Hospital Campus Decking- Bonsall Av
Completed April 29 – May 2

## Slide 89
Westwood/VA Hospital 405 Ramps Closure for Decking
Dates: May 13 to 16
and May 20 to 23
Hours: 9pm, Fri through 5am, Mon
Closures:
Westbound Wilshire Bl to southbound I-405 on-ramp will be closed.
Southbound I-405 to eastbound Wilshire Bl off-ramp will be closed.
*Construction is dynamic and subject to change​.​

## Slide 90
Westwood/VA Hospital Upcoming Waterline Work
Wilshire Blvd
Federal Ave
Traffic Control:
VA Hospital access will be detoured nightly along Sepulveda Bl and Santa Monica Bl to Sawtelle Bl and Dowlen Dr.
Where: Wilshire Bl, Federal Av, and Bonsall Av
When: Summer of 2022*
Work Hours: Vary depending on the work scheduled in each stage.
Monday to Friday, 9am to 3:30pm, 7pm to 6am, Monday to Sunday, and 11pm to 6am, Monday to Sunday.
*Construction is dynamic and subject to change​.​
Click to add text

## Slide 91: VA Mural Project History
1995: Artist and U.S. Navy veteran, Peter Stewart, with donated art materials and volunteers envisioned and created a tribute mural near the VA Greater Los Angeles Healthcare Center in Westwood. The specific area eventually selected was the underpass at the intersection of Bonsall Ave and Wilshire Blvd, north of the West LA VA Medical Center Campus.
Stewart died before the mural was fully completed. The mural remained unfinished, but it has become a treasured and honored landmark for veterans and VA staff.
2012: Metro’s Purple Line Extension Final EIR/EIS in 2012 assumes that the mural could be protected in place during construction. However, subsequent studies show that removal of the northeast mural is necessary to build key Westwood/VA Medical station design elements. Attempting to rescue the mural is deemed unfeasible due to existing wall conditions.

## Slide 92: VA Murals to Remain in Place

## Slide 93: VA Legacy Art Mural
Project planners found that there is not sufficient space to accommodate the mural in its original location.
Therefore, plans were developed to decommission approximately 115 feet of the 23,000 square foot mural during the construction of the north entrance to the Westwood/VA Metro Station.
Only portion of mural to be removed is located at the westbound Wilshire Blvd off-ramp to Bonsall Ave.
Impacted Section of the Mural

## Slide 94: VA Legacy Art Mural

## Slide 95
Shad Meshad, founder, National Veterans Foundation

## Slide 96: Engaging the Veteran Community
To honor this section of the mural, Metro will engage the services of an arts organization to work with the veteran community on a Veterans Legacy Art Project.
Veterans will participate throughout the design process that will lead to a mosaic mural to be installed across the street from the original.
Final design will be determined with veteran involvement and input.
Outreach and Engagement scheduled for 2024.
Removal of mural wall scheduled for 2025.

## Slide 97
Stay in touch
Eat Shop Play has highlighted local businesses along the Purple Line Extension project in Koreatown, Miracle Mile, Beverly Hills, Century City, and Westwood, especially eateries and specialty businesses operating pick-up and delivery during the past months.
The Eat Shop Play program continues supporting local businesses as construction progresses by promoting them through regular social media posts and newsletters.

## Slide 98
Stay in touch
Jeong Yuk Jeom
621 S Western Ave #100
​ Cook your own premium cut beef Korean BBQ in Koreatown​
Business hours​ Open 7 days a week 11am-10pm
​
Jeongyukjeom.com
(213) 384-2244

## Slide 99
Stay in touch
Wilshire Beauty
5377 Wilshire Bl
​ World-class family-operated beauty supply in Miracle Mile since 1947
Business hours​ Mon – Sat: 10am – 5pm
Wilshirebeauty.com
(323) 937-2001
Notes: The Kohan family, proprietors of Wilshire Beauty, curates the most exclusive collection of American, European, and Japanese crèmes, lotions, mousses and applications found anywhere and bring the world’s finest beauty products under one roof.

## Slide 100
Stay in touch
M Day Spa
8326 Wilshire Bl
​ Indulge in beauty; Med-Spa in Beverly Hills
Business hours​ Mon - Fri: 10am - 6pm
Sunday: 10am - 5pm
​
themdayspa.com
(310) 657-8081
Notes: The M Day Spa offers an extensive list of treatments ranging from massages, age reversal skin peels, lashes and brows, facials, face lifts, and more. Visit online for a full list of services and to book an appointment.

## Slide 101
Stay in touch
Mystic Flowers and Gardens
1925 Century Park East, Suite M
​ Beautiful and fresh flower arrangements in Century City.
Business hours​ In-store Mon-Fri: 10am - 3pm
​
mysticflowersandgardens.com
(310) 284-3417

## Slide 102
Stay in touch
Float Lab
1025 Westwood Bl, Suite B
​ A unique sensory deprivation experience in Westwood
Business hours​ Tue – Fri: 11am – 9pm Sat – Sun: 8:30am-9pm​
floatlab.com
(310) 208-0000
Notes: Meet yourself: In the light-free, sound-resistant, zero-gravity environment, the mind can redirect its thoughts and focus inward.
Perfect and unique Mother's Day gift. Book mom a session and literally give her 2 hours of peace and quiet to herself.

## Slide 103
Stay in touch
Contact Us
> For more information on Eat Shop Play visit​
metro.net/eatshopplay ​
> Send an email to eatshopplay@metro.net

## Slide 104
Business Interruption Fund (BIF)

## Slide 105: Metro’s Business Interruption Fund
BIF Information and Eligibility
Financial assistance to small “mom & pop” businesses with 25 or fewer full-time employees directly impacted by Metro Rail construction along three project areas​:
  Crenshaw/LAX Transit Project​
  Purple Line Extension, Sections 1, 2 & 3​
  Regional Connector Project, Little Tokyo area & 2nd/Broadway Segment*
Businesses must be located immediately adjacent to the rail corridor and meet other eligibility requirements​
Grant amounts are determined by business revenue loss directly related to period of Metro construction disruption​
Businesses may receive up to $50,000 per impact year
*Segment eligibility based on full street closure with duration greater than six continuous months. Eligibility ended 6/30/17.​

## Slide 106
Metro’s Business Interruption Fund
Metro’s Business Interruption Fund (BIF) is accepting applications for transit rail construction impact along the Crenshaw/LAX Transit Project, the Little Tokyo area of the Regional Connector and Sections 1, 2 and 3 of the Purple Line Extension sustained from March 20, 2020, forward (during the COVID-19 pandemic).
Small “mom and pop” businesses that experienced transit rail construction impact during the COVID-19 pandemic may be eligible.
Potentially eligible small business owners may contact BIF Fund Administrator Pacific Coast Regional at 213.739.2999 x223 or Metro at bif@metro.net.
Metro does not cover revenue loss nor fixed operating expenses related to COVID-19 impacts.

## Slide 107
Metro’s Business Interruption Fund
Chart: 
| Crenshaw/LAX Transit Project | Purple Line Extension Section 1 | Purple Line Extension Section 2 | Regional Connector, Little Tokyo Area | Regional Connector, 2nd/Broadway Segment
Total Grant Amount | 15090988.93 | 5485204.34 | 2111053.94 | 1996164.16 | 950164.03
  *BIF Grants do not cover COVID-19 related impacts.
Value of BIF Grants Awarded:
$34,141,560.28*

## Slide 108
Stay in Touch
Upcoming Meeting Dates
May 10: Section 3, Decking Information
June 1: Beverly Hills stations - Sections 1 and 2
All meetings use: https://zoom.us/j/96626476708
Link to webinars available at metro.net/purple
213.922.6934
purplelineext@metro.net
metro.net/purple
@purplelineext
facebook.com/purplelineext