## Slide 1: We will get going in just a moment

## Slide 2: Thank you for joining us!

## Slide 3
Metro Fares on Election Day Go Metro to vote! Metro is offering free rides on all buses, trains, Metro Micro and Bike Share on Election Day, Tuesday, November 8. The free rides will run from midnight to 11:59pm on November 8. Learn more at metro.net/govote.

## Slide 4: Agency News
Let's Ride Safety Together Keeping riders safe is our number one priority and we're committed to providing you with a great experience on Metro. That's why we've launched a plan that reimagines the way we approach public safety, to ensure all our riders feel safe, comfortable, and welcome on our system. Check out 'Let's Ride Safely Together’ at https://www.metro.net/riding/safety-security/ to learn how we're improving security, cleanliness, and customer care on our buses and trains.

## Slide 5: Public Hearing: November 14, 2022
Metro will hold a public hearing on Monday, Nov. 14, at 5pm to get community input on potential fare changes and invites riders to learn more about how they can save under the new structure.
Metro will implement fare capping– an equitable, pay-as-you-go fare payment model that ensures customers only pay for the rides they take and never overpay.
With fare capping, the Metro 1-Day, 7-Day and 30-Day passes, as well as internal transfers, would no longer be necessary.
https://www.metro.net/simplefares

## Slide 6: Presentation Panelists
Metro Purple Line Extension Team
Marlon Walker, Community Relations Manager
  Sections 1, 2 & 3 and Division 20
Ned Racine, Principal Community Relations Officer
  Section 1 and Division 20
  Mindy Lake, Principal Community Relations Officer
  Section 1, Beverly Hills and Section 2
Metro Arts and Community Enrichment
Clare Haggarty, Senior Manager, Transportation Planning
Erik Qvale, Manager, Creative Services
Metro New Media Team​
Ginny Brideau, Manager, Community Relations New Media Team
Stephanie Molen, Principal Community Relations Officer New Media Team
Contractor Representatives and Presenters
Scott Donohue, STS Community Relations Coordinator
Matt Evans, TPOG Project Information Coordinator
Joanna Amador-Dempsey, Modern Times Community Relations Director
Metro Business Interruption Fund Team
Eric Chun, Sr. Transportation Planner (Interim)

## Slide 7: Today's Agenda
  Project Overview
  Division 20 Section 1 Construction Update Section 2 Construction Update Section 3 Construction Update
  Eat Shop Play
  Business Interruption Fund

## Slide 8
Purple Line Extension Alignment

## Slide 9
Sections 1, 2, & 3 Status
*Subject to change. The PLE project team is working to deliver the project consistent with Measure M.
 | Forecasted Schedule |  | 
Section | Section 1 | Section 2 | Section 3
Length | 3.92 Miles | 2.59 Miles | 2.56 Miles
New Stations | Wilshire/La Brea Wilshire/Fairfax Wilshire/La Cienega | Wilshire/Rodeo Century City/ Constellation | Westwood/UCLA Westwood/VA Hospital
Pre-Construction Activities | 2014 – 2015 | 2016 – 2018 | 2018 – 2019
Construction | 2015 – 2024 | 2018 – 2025 | 2019 – 2027
Operations | 2024 | 2025 | 2027

## Slide 11: Project Overview
  Operational improvements to Metro’s Division 20 Rail Yard will accommodate increased service levels on the Metro Red and Purple (B and D) Lines
  Improvements include:
    Widening of heavy rail portal
    New turnback facility
    Expansion and reconfiguration of rail storage tracks
Benefits
  Faster and more frequent service
Arts District Project Area
One Santa Fe
Tunnel Portal
Turnback Facility
Storage Tracks

## Slide 12: Current work- Portal Area
Before Construction
Bing Image
Current area*
*Delineations on the image are not to scale.

## Slide 14: Wilshire/La Brea Station Rendering

## Slide 15
Wilshire/La Brea Station Box
Outline of the Wilshire/La Brea underground station box on Wilshire Bl. from Orange Dr. to Detroit St.

## Slide 16: La Brea Station – Post Decking Restoration
Curb, Gutter, Bus Pad Restoration
Following deck removal, a work zone has been established on the north side of Wilshire Blvd. between Mansfield Ave. and La Brea Ave.
Work zone supports:
Curb and gutter restoration
Streetlight installation
Tree well installation
Wheelchair and bus lane
completion
Starting: July 2022
Duration: approximately 4 months
*Dates Subject to Change
Sycamore Restoration Orange Restoration
A traffic control plan for this phase of street restoration is being developed. More specific information will be available later this year.

## Slide 17: La Brea Station – South Side Civil Restoration
Curb, Gutter, Bus Pad Restoration
Following north side restoration, a work zone will be established on the south side of Wilshire Blvd. between Mansfield Ave. and Detroit St.
Work zone supports:
Curb and gutter restoration
Streetlight installation
Tree well installation
Wheelchair and bus lane
completion
A traffic control plan for this phase of street restoration is being developed. More specific information will be available later this month.

## Slide 18: Work Behind the K-Rail
Finished Bus Pad and Curb at Wilshire/Orange
Finished Bus Pad and Curb on Wilshire – between Orange Dr and Sycamore Av

## Slide 19: Wilshire/Fairfax Station Rendering

## Slide 20
Fairfax Decking Removal - Sequence
Weekend | Dates
1 | October 7 – October 10
2 | October 14 – October 17
3 | October 21 – October 24
4 | October 28 – October 31
(No Work) Local Event | November 4 – November 7
5 | November 11 – November 14
6 | November 18 – November 21
Thanksgiving (No work) | November 25 – November 28
7 (Holiday Moratorium Exemption Requested) | December 2 – December 5
Holiday Moratorium Period (No Work) | December 9 – December 12
Holiday Moratorium Period (No Work) | December 16 – December 19
Christmas (No work) | December 23 – December 26
New Year’s (No work) | December 30 – January 2
8 | January 6 – January 9
9 | January 13 – January 16
10 | January 20 – January 23
11 | January 27 – January 30
12 | February 3 – February 6
13 | February 10 – February 13

## Slide 21: Fairfax Decking Removal – Phase 1
Work will begin at 9pm on Friday night and continue through 6am on Monday morning. As a contingency, the design-builder has requested approval to extend work hours as late as 12 noon on Monday. The extension will only be used in the event of an emergency.
Decking Removal will begin at the Wilshire/Fairfax Station over the weekend of October 7 to October 10.
Phase 1, the area immediately east of Fairfax Av, will be the first section restored.
A full closure on Wilshire Bl will be in place over the duration of this work. Eastbound traffic will be detoured at Fairfax Av, and westbound traffic will be detoured at La Brea Av
Weekend | Dates
1 | October 7 – October 10
2 | October 14 – October 17
3 | October 21 – October 24
4 | October 28 – October 31
(No Work) Local Event | November 4 – November 7
5 | November 11 – November 14
6 | November 18 – November 21
Thanksgiving (No work) | November 25 – November 28
7 (Holiday Moratorium Exemption Requested) | December 2 – December 5

## Slide 22: Fairfax Decking Removal – Phase 1 Detour Map
Eastbound Wilshire > Northbound Fairfax Av > Eastbound 6th St > Southbound La Brea Av > Eastbound Wilshire
Westbound Wilshire > Westbound 6th St > Southbound Fairfax Av > Westbound Wilshire

## Slide 23: Fairfax Decking Removal – Phase 2
Weekend | Dates
8 | October 28 – October 31
9 | November 4 – November 7
Work will begin at 9pm on Friday night and continue through 6am on Monday morning. As a contingency, the Design-Builder has requested approval to extend work hours as late as 12 noon on Monday. The extension will only be used in the event of an emergency.
Following Phase 1 Decking Removal, STS will begin working within the Wilshire/Fairfax Intersection.
This work will take two weekends to complete, October 28 – October 31, and November 4 to November 7
Full closures will be in place on Wilshire Bl and Fairfax Av. All traffic will be detoured around the workzone.
Southbound Fairfax Av traffic will be detoured at 6th St
Northbound Fairfax Av traffic will be detoured at Olympic Bl
Eastbound Wilshire Bl traffic will be detoured at La Cienega Bl and San Vicente Bl
Westbound Wilshire Bl traffic will be detoured at La Brea Av

## Slide 24: Fairfax Decking Removal – Phase 2 Detour Map
Eastbound Wilshire > Southbound La Cienega Bl> Westbound Olympic Bl > Northbound La Brea Av > Eastbound Wilshire
Eastbound Wilshire > Southbound San Vicente Bl > Northbound La Brea Av > Eastbound Wilshire
Westbound Wilshire > Southbound La Brea Av > Westbound Olympic Bl > Northbound San Vicente Bl > Westbound Wilshire
Northbound Fairfax Av > Eastbound Olympic Bl > Northbound La Brea Av > Westbound 6th St > Northbound Fairfax Av
Southbound Fairfax Av > Eastbound 6th St > Southbound La Brea Av > Westbound Olympic Bl > Southbound Fairfax Av

## Slide 25: Fairfax Decking Removal – Phase 3
Weekend | Dates
Veteran’s Day (No work) | November 11 – November 14
10 | November 18 – November 21
Thanksgiving (No work) | November 25 – November 28
11 | December 2 – December 5
12 | December 9 – December 12
13 | December 16 – December 19
Work will begin at 9pm on Friday night and continue through 6am on Monday morning. As a contingency, the Design-Builder has requested approval to extend work hours as late as 12 noon on Monday. The extension will only be used in the event of an emergency.
Following Phase 2 Removal, the third and final phase of work will begin to the west of Fairfax Av
This work will take place over 4 weekends, beginning on November 18.
Full closures will be in place at Fairfax Av and San Diego Way
Eastbound Wilshire will be detoured at La Cienega Bl or San Vicente Bl
Westbound Wilshire will be detoured at Fairfax Av

## Slide 26: Fairfax Decking Removal – Phase 3 Detour Map
Eastbound Wilshire > Southbound La Cienega Bl > Eastbound Olympic Bl > Northbound La Brea Av > Eastbound Wilshire
Eastbound Wilshire > Southbound San Vicente Bl > Northbound La Brea Av > Eastbound Wilshire
Westbound Wilshire > Southbound Fairfax Av > Northbound San Vicente Bl > Westbound Wilshire

## Slide 27: Fairfax Station – Decking Removal
Excavators and haul trucks will be utilized during backfilling operations.
Dozens of trucks will be used each weekend to haul steel, decking panels, and SOE out of the area.
Large cranes and other heavy equipment will lift the steel beams and deck panels out of the ground.

## Slide 28: Fairfax Station – Decking Removal
Following decking removal, steel beams and SOE haul out, and backfilling and utility placement, a new street surface will be placed from curb to curb.
Work will progress east to west, from one weekend to the next.

## Slide 29: La Brea Station – Decking Removal Equipment
Aboveground
Cranes
Haul trucks, dump trucks
Concrete pump
Loaders
Saw cutter, jackhammer
Vibrator, roller
Belowground
Compact excavators
Compact bulldozers
Man lifts, forklifts
Graders
Loaders

## Slide 30: Fairfax Station – Decking Removal Schedule
* Subject to Change

## Slide 31: Fairfax Station – Decking Removal Sequence (Part 1)
Activity | Occurs
Design-builder begins to remove deck panels along Wilshire Blvd. | Once road is closed to traffic (9pm)
Crews begin removing steel beams and support for excavation above the station | All day Saturday
Utilities will be relocated as needed. Trucks loaded with backfilling materials will be staged around the deck openings. | Saturday
Testing and quality assurance conclude prior to asphalt placement | All day Sunday

## Slide 32: Fairfax Station – Decking Removal Sequence (Part 2)
Activity | Occurs
Asphalt placement | Begins after backfilling (asphalt requires approximately four hours to cure/cool before it can carry weigh)
City agencies test asphalt to ensure that it will be safe for commuters | After curing
The final steps of decking removal includes striping, removing traffic control devices, and opening the road | Sunday night and Monday morning

## Slide 33: Outreach Schedule
Outreach | Occurs
STS and Metro discusses closures with Council District 5. | May 2022
Affected residents and business owners invited to online meetings to discuss decking removal. Meeting announcement appears on Weekly Look Ahead. | One month before work begins
Wilshire/Fairfax decking removal presented during quarterly webinar. | One month before work begins
Door-to-door outreach conducted. A Construction Notice will be widely distributed adjacent to the Wilshire/La Brea intersection. | One month before work begins
A Construction Notice will be re-issued on the Metro website and distributed to the Metro Email List. Computer message signs will be placed at the work area. | One week before work begins
A Construction Notice describing the work will be sent in the Weekly Look Ahead email. | Weekly

## Slide 34
Wilshire/La Cienega Station Rendering

## Slide 35
Wilshire/La Cienega Station Backfilling
*Subject to Approval
When: Continuing in November 2022
What: Station Backfilling
This is the first of multiple construction activities in advance of decking removal and street restoration.
Why: The Station Roof is approximately 20ft below the street surface. That area will need to be filled with slurry, soil, and utilities.
  STS will need to restore utilities in the street, including sewer, storm drains, and other utilities.
Traffic Control and Work Hours: Intermittent weeknights and weekend days.
  Hours: 8pm to 6am (the following morning) on weeknights
  Hours: 6am to 6pm on Saturdays
  Traffic Control: Wilshire Bl reduced to a single lane in each direction between San Vicente Bl and Le Doux Rd
Backfilling operations at Wilshire Bl and Orange Dr, within the City of Los Angeles

## Slide 36
Wilshire/La Cienega Station Appendage Work
Why: Multiple appendages will be required for each station on the Purple Line Extension
Each appendage structure houses a vital function for the stations:
  Emergency exits
  Utility rooms
  Ventilation rooms
  Entrance and exit structures
When: Began in March 2021 through 2023*
Where: Information about specific traffic control and work hours will be available in future community meetings and construction notices
Coordination with impacted businesses will be conducted prior to the start of the next phase of appendage work

## Slide 37
Wilshire/La Cienega Station: Appendage Structures Phase 1A
Appendages – Northeast
Appendage – Main Entrance
Phase 1A
Phase 1A
Station Box
Station appendage locations

## Slide 38
Wilshire/La Cienega Station Appendage Work
*Dates subject to change.
Phase 1A Traffic Control (March 2021 through November 2022)*
Wilshire Blvd. between San Vicente Bl and La Cienega Bl reduced to two lanes in each direction.
Left turns from Wilshire Bl onto Gale Dr will be restricted from both directions. Left turns from Tower Dr onto westbound Wilshire Bl will be restricted.
The east/ west crosswalks at Gale will be maintained.
The north sidewalk between San Vicente Bl and Gale Dr will be closed during this phase of work. A pedestrian detour for east/west travel will be in place on the south side of Wilshire. Access to 8383 Wilshire will be maintained.
The loading zone in front of the Saban Theatre on Wilshire Bl will be closed over the duration of this closure.
Daily closures on Gale Dr will continue as needed. Access to N Gale Dr will be maintained from San Vicente Bl

## Slide 39
Wilshire/La Cienega Station Appendage Structures Phase 2
*Dates subject to change.
Appendage – South Gale
Appendages –
Southwest
Phase 2
Phase 2
Station Box
Station Box
Phase 2 Traffic Control (December 2022 through July 2023)*
  Wilshire Blvd. between San Vicente Blvd. and La Cienega Blvd. reduced to two lanes in each direction
  Through traffic on southbound Gale Dr. through the Wilshire/Gale intersection will be intermittently restricted.
  Left turns from Wilshire Blvd. onto Hamilton Dr. and Gale Dr. will be restricted.
  Additional details will be available in a future community presentation and project construction notices.

## Slide 40
Wilshire/La Cienega Station: Appendage Structures Phase 1A

## Slide 41: Replacement Parking
Locations for One Hour Free Parking: Mon to Fri, 10am to 3pm
  8447 Wilshire Bl: Accessible from N Hamilton
  8350 Wilshire Bl: Accessible from S Tower
  Please mention "Metro" upon entering the building to receive the 1st hour free

## Slide 42
Concrete and Material Deliveries
Traffic Control:
  Westbound Wilshire Bl will be intermittently reduced to one lane between San Vicente Bl and Hamilton Dr
  Daily closures will be utilized in support of ongoing work activities in the staging yard at Gale Dr
Deck Panel Access – Hamilton Dr (9am to 4pm & 8pm to 7am, weekdays; 7am to 6pm, Saturdays)
  Continuing in October, intermittent deck panel access may be implemented within the Wilshire/Hamilton intersection.
  Wilshire will be reduced to a single lane in each direction between Tower Dr and Stanley Dr
  Left turns from Wilshire to Hamilton will be restricted. Through traffic on Hamilton will be restricted at Wilshire.
Outside Gale Staging Yard
Noise Mitigations: will remain in place
  Sound blankets around noisy equipment
  Trucks equipped with low-impact backup alarms
  Nylon straps used to lift material

## Slide 43
Next Steps: Station Construction
Construction of station roof will continue through 2022
Each roof placement will be 60 feet by 60 feet
Work activities in support of concrete and deliveries will be conducted within the staging yards, and occasionally on Wilshire Bl
Daily construction activities may be conducted underneath Wilshire Bl and from both Staging Yards for 24 hours a day
Illustration of station interior design

## Slide 44: Wilshire/La Cienega Station Progress
Looking East
Looking West

## Slide 45: Wilshire/La Cienega Station Progress
Looking East
Photo courtesy of Ken Karagozian

## Slide 46
Instrumentation Work
When: Ongoing in 2022
Traffic Controls:
  Intermittent lane reductions on Wilshire Bl, La Cienega Bl, and side streets during off-peak hours may be in place to support the maintenance of geotechnical instruments in the Wilshire Bl and La Cienega Bl area
  Intermittent lane reductions may be in place on Wilshire Bl, west of La Cienega Bl, to support coring survey work under Wilshire Bl
Additional details on this work will be available in future construction notices
Example of instrumentation drilling

## Slide 48: Section 2: Station Naming
bit.ly/3KHqNgs

## Slide 49
Wilshire/Rodeo Station Rendering

## Slide 50
Wilshire/Rodeo Station Box
Rendering shows length of the underground station box on Wilshire Bl from Cañon Dr to Beverly Dr

## Slide 51
Wilshire/Rodeo Station: Permitted Work Hours and Traffic Control
Work hours underneath the deck are 24 hours a day, 7 days a week. Deliveries of material, equipment, and concrete will be ongoing daily from Wilshire Bl. A breakdown of daily work hours on street level:
  From 7am to 9am and 4pm to 8:15pm, Wilshire Blvd. will remain open with three lanes in each direction between El Camino Dr. and Crescent Dr.
  From 9am to 4pm, Wilshire Blvd. may be reduced to two lanes in each direction between El Camino Dr. and Crescent Dr.
  From 8:15pm to 7am, Wilshire Blvd. may be reduced to one lane in each direction between El Camino Dr. and Crescent Dr.
Traffic control may also be implemented on Beverly Dr. At least one through traffic lane will be maintained in both directions between 9am-4pm and 8pm-7am.
From 9am to 4pm, S. Reeves Dr. may be reduced to one lane northbound. A flagger will be on site to assist motorists with 2-way traffic.

## Slide 52: Wilshire/Rodeo Station: Structure Construction through 2024

## Slide 53: Wilshire/Rodeo Station: Concourse Level Activity
Concourse level progress | Shoring & Walls

## Slide 54: Wilshire/Rodeo Station: Construction Progress
Entrance Wall progress.

## Slide 55
Wilshire/Rodeo Station Holiday Moratorium
A moratorium to construction activity outside of the station will be in effect beginning on Thanksgiving Day (11/24/2022) through New Years Day (1/1/2023).
  During this time, the contractor will work within the station to continue progressing with station construction.
  Work outside of the station will resume its normal schedule beginning on Tuesday, January 3, 2023.

## Slide 56
Upcoming Work | SCE Installation
Where: Wilshire Blvd. between Dayton Way and Rexford Dr.
  Starting east of station box
Duration: Approximately 7-8 months [Work started Saturday, September 10]
  Starting east of station box from S Canon Dr to Rexford Dr (Sep – Nov) Shift to west side after
  After completion east of S Canon Dr, shift to west of the station from Dayton Way to Beverly Dr.
Work Hours: Weekends, 8am to 8pm | Weekdays 8:15pm to 7am
Traffic Control:
  Wilshire Blvd. may be reduced to one lane in each direction overnight and on weekends
Contractor is progressing with installation of SCE Permanent Power Feeds to the station.

## Slide 57
Upcoming Ground Improvement/Cross Passage Work
The contractor is progressing with ground improvement work along the tunnel alignment in preparation for the construction of cross passage tunnels.
When: Work started in late May
  Ongoing until early 2023
Where: *14 locations; First 7 work sites noted on map
Work Hours: Monday-Friday 8am-11pm on Wilshire Bl.
  Closures remain in place 24/7 until each location is completed
Duration: 2-4 weeks/location
*Additional notices detailing dates & closure information will be provided in advance

## Slide 58
Upcoming Ground Improvement/Cross Passage Work
*Additional notices detailing dates & closure information will be provided in advance
Final locations to be completed after holiday moratorium.

## Slide 59: Cross Passage Work – Sidewalk Enclosures
Sidewalk enclosures are placed at each cross passage location to house equipment.
Each enclosure remains up until the completion of cross passage construction below ground.
  Approximately 3 - 4 months

## Slide 60
Wilshire/Rodeo Station: Geotechnical Instrumentation
Where: Instruments will be installed within the tunnel alignment and station box area to monitor ground movement, settlement and other geological conditions
  Installations will be within the public right of way and within privately owned properties
Duration: Ongoing
Work Hours On Wilshire Bl:
  Weekdays, 7am to 4pm and 8pm to 7am
Work Hours Off Wilshire Bl:
  Weekdays, 8am to 6pm and 8pm to 7am
Example of 10-foot geotechnical instrumentation pole.

## Slide 61: Tunnel Boring Machine (TBM) Update
Tunneling Statistics As of (10/12/2022) | 
Ruth | 11,510 feet (total journey) 90% complete
Harriet | 11,510 feet (total journey) 95% complete
Both TBM’s have passed through the Wilshire/Rodeo Station
Will continue mining east towards Wilshire/La Cienega
Tunneling Duration: Approximately 2 years from the start
Remaining Duration: ~2 months

## Slide 62: Century City/Constellation Station Rendering

## Slide 63
Century City/Constellation Station Box
Length of the underground station box on Constellation Blvd.
from Century Park East to Avenue of the Stars.

## Slide 64: Station Excavation
Excavation of the underground station underneath Constellation Blvd. is in progress and will continue until reaching approximately 100 feet in depth.
Work Hours: 24 hours a day, 5 days a week (Monday – Friday)
Anticipated Completion: 1st quarter 2023
Temporary partial traffic lane closures may be required on Constellation Blvd. both east and west of Avenue of the Stars to facilitate this work.
Station looking East
Notes: CCS Station Looking East (Looking up at utilities from station invert) East side excavation at 100 ft. West side excavation at 50 ft.

## Slide 65: Station Entrance Excavation
Notes: CCS Station Looking SW

## Slide 66: Station Entrance Excavation
Notes: Looking into the excavation to show current depth.

## Slide 67: Sanitary Sewer and Storm Drain Relocation
Ongoing: Work activity began in March 2022
Anticipated Duration: End of January, 2023
Anticipated Traffic Control:
  Lane closures on Avenue of the Stars
  Night closures (8pm to 6am) will be required intermittently

## Slide 68: Stage 8 (Current Steady State Closures)
Anticipated Completion Date: End of January 2023
Work Hours: 24 hours a day, 7 days a week
What to Expect: Potholing, piling, shoring, and utility installation
Work Area
Work Area
Driveway open
Driveway open
Driveway open
Delivery driveway open
Intermittent closure
Traffic Control:
  Left turns restricted on NB AOS onto WB Constellation Bl
  Intermittent closure of access lane on south side of Constellation Bl.

## Slide 69: Stage 8.1
Anticipated Duration: Intermittently during Stage 8
Work Hours: 8pm to 6am
What to Expect: Potholing, piling, shoring, and utility installation
Driveway open
Driveway open
Driveway open
Delivery driveway open
Intermittent closure
Traffic Control:
  Left turns restricted on SB AOS onto EB Constellation Bl
  Intermittent closure of access lane on south side of Constellation Bl.
Night-time additional closure

## Slide 70: Stage 7B (Steady State Closure)
Anticipated Duration:
  2 years (Re-implemented after utility relocation)
Traffic Control:
  One eastbound and westbound lane are accessible from CPW to AOS
  Maintaining access to Westfield driveways and Fairmont Century Plaza Hotel
Driveway open
Driveway open
Driveway open
Delivery driveway open

## Slide 72
Section 3 Tunnel From Century City to Westwood

## Slide 73
Section 3 Tunneling Progress
Aura (TBM 2)
Iris (TBM 1)
9,436 feet
69.8% complete
10,532 feet
78% complete
Tunneling Statistics
as of 10/30/2022
Future Station Boxes

## Slide 74
Westwood/UCLA Station Rendering (Northwest Entrance)

## Slide 75
Westwood/UCLA Station Rendering (Northeast Entrance)

## Slide 76: Westwood/UCLA Station Rendering (Southeast Entrance)

## Slide 77
Westwood/UCLA Station Box
Rendering shows length of the underground station box on Wilshire Bl between Westwood Bl and Veteran Av.
Construction continues in UCLA Lot 36. Some work may overlap onto the sidewalk.

## Slide 78: Decking
Decking is a process where the street is excavated from curb to curb at a depth of about 10 to 12 feet. The deck beams are installed over the piles that have been installed. The concrete precast panels are place over the piles and create a temporary street surface. The panels get restriped for vehicular and pedestrian use.
Temporary partial street closures will be implemented on Wilshire Bl. Traffic will be detoured around the construction work.
Closures will occur on continuous weekends, Friday to Monday, 11 pm to 6am.
Preparation work occurs from 9pm to 11 pm and 11pm to 2 am.
Decking anticipated for 13 continuous weekends.

## Slide 79: Westwood/UCLA Station Decking

## Slide 80
Decking Progress Westwood/UCLA Station
Click to add txt

## Slide 81: Decking on Wilshire Bl between Veteran Av and Westwood Bl.

## Slide 82: Decking Traffic Control
Eastbound Wilshire Bl traffic access maintained with two lanes of traffic.
Westbound Wilshire Bl traffic detoured at Westwood either to Kinross Av or Ohio Av.
Northbound and Southbound traffic maintained through Stage 4 Veteran Av and Gayley Av.
SB Westwood Bl closed to traffic.
*Traffic control plans pending approval

## Slide 83: Holiday Moratorium Exemption
The holiday moratorium applies typically from November 25 through January 1. An exemption allows for a continuance with construction activities during the holiday season. TPOG will be requesting exemptions to allow construction to continue for both stations this year.
Coordination will occur with Council District 5, Council District 11, Bureau of Engineering (BOE), LA Department of Transportation (LADOT) and LA Board of Public Works.
Continued work will ensure the construction schedule is maintained.
No work on Thanksgiving Day (November 24 and 25), Christmas Day (December 25) and New Year's Day (January 1st).

## Slide 84: Excavation and Support of Excavation Activities in Lot 36
Excavation for the Westwood/ UCLA station has begun at Lot 36 and will continue for approximately six months. The work during this period includes mass excavation, hauling, bracing installation, lagging, and station ventilation installation. The work will happen primarily underground. Hauling of materials will also occur throughout the day by using the driveways on Veteran Av Wilshire Bl.
Where: Lot 36
When: November 1, 2022, to April 2023
Work Hours:
Excavation: 7pm to 6am and 6:00am to 4:30pm, Monday through Sunday
Hauling: 9pm to 5:30am, Monday through Sunday
Support of Excavation Activities: 6:00am to 4:30pm, Monday through Sunday,

## Slide 85: Installation of Storm Drain Catch Basins
Install storm drain catch basins for the future Westwood/UCLA Station began on October 24. The work will require eastbound lane reductions on Wilshire Bl between Veteran Av and Westwood Bl for approximately 2 weeks. There will be no impact to utilities.
Where: Eastbound Wilshire Bl between Veteran Av and Westwood Bl.
When: October 24 to November 30, Weekdays
Work Hours: 9pm to 6am

## Slide 86: Temporary Power Support
Preparation of temporary power for excavation of the future Westwood/UCLA Station. Work will occur on Wilshire Bl and Gayley Av/ Midvale Av for approximately three weeks, Monday to Friday. Eastbound Wilshire Bl lanes will be reduced between Veteran Av and Westwood Bl. No thru traffic at the intersection of Wilshire Bl and Gayley Av/Midvale Av. The south leg crosswalk will be closed.
Where: Gayley Av/Midvale Av and Wilshire Bl.
When: November 2022 to February 2023
Work Hours: 9pm to 6am, Monday to Friday

## Slide 87: Westwood/VA Hospital Station Rendering

## Slide 88
Westwood/VA Hospital Station Rendering (Bonsall Av)

## Slide 89
Westwood/VA Hospital Station Box

## Slide 90
Instrumentation Installation
Instrumentation installation around the VA Station will continue through June 2023.
*Construction is dynamic and subject to change​.​

## Slide 91: Excavation and Support of Excavation
Excavation for the Westwood/ VA Hospital station has begun at Lot 42 and the West of Bonsall Av staging yard and will continue for approximately eight months on weekdays. The work during this period includes mass excavation, hauling, bracing installation, lagging, and station ventilation installation.
Where: Lot 42 and West of Bonsall Av staging yard
When: October 24, 2022 through June 30, 2023
Work Hours:
Excavation: 9pm to 6am, Weekdays (Weekends - Optional)
Hauling: 9pm to 6am
Support of Excavation Activities: 6am to 6pm

## Slide 92
Westwood/VA Hospital Upcoming Waterline Work
Wilshire Blvd
Federal Ave
Traffic Control:
VA Hospital access will be detoured nightly along Sepulveda Bl and Santa Monica Bl to Sawtelle Bl and Dowlen Dr.
Where: Wilshire Bl, Federal Av, and Bonsall Av
When: Winter of 2023*
Work Hours: Vary depending on the work scheduled in each stage.
Monday to Friday, 9am to 3:30pm, Monday to Sunday, 7pm to 6am, and Monday to Sunday, 11pm to 6am.
*Construction is dynamic and subject to change​.​

## Slide 93
Piece by Piece

## Slide 94: VA Mural Project History
1995: Artist and U.S. Navy veteran, Peter Stewart, with donated art materials and volunteers envisioned and created a tribute mural near the VA Greater Los Angeles Healthcare Center in Westwood. The specific area eventually selected was the underpass at the intersection of Bonsall Ave and Wilshire Blvd, north of the West LA VA Medical Center Campus.
Stewart died before the mural was fully completed. The mural remained unfinished, but it has become a treasured and honored landmark for veterans and VA staff.
2012: Metro’s Purple Line Extension Final EIR/EIS in 2012 assumes that the mural could be protected in place during construction. However, subsequent studies show that removal of the northeast mural is necessary to build key Westwood/VA Medical station design elements. Attempting to rescue the mural is deemed unfeasible due to existing wall conditions.

## Slide 95: VA Murals to Remain in Place

## Slide 96: Veterans Legacy Art Project
Project planners found that there is not sufficient space to accommodate the mural in its original location.
Therefore, plans were developed to decommission approximately 115 feet of the 23,000 square foot mural during the construction of the north entrance to the Westwood/VA Metro Station.
Only portion of mural to be removed is located at the westbound Wilshire Blvd off-ramp to Bonsall Ave.
Impacted Section of the Mural

## Slide 97: Veterans Legacy Art Project

## Slide 98
Shad Meshad, founder, National Veterans Foundation

## Slide 99: Engaging the Veteran Community
To honor this section of the mural, Metro has engaged the services of arts organization, Piece by Piece, to work with the veteran community on the Veterans Legacy Art Project.
Veterans can participate throughout the design process that will lead to a mosaic mural to be installed across the street from the original.
Final design will be determined with veteran involvement and input.
Outreach and Engagement is happening now through Jan 2023.
Removal of mural wall scheduled for 2025.

## Slide 100: How to participate: Contact Piece by Piece Email jadie@piecebypiece.org or Call 213.549.1420

## Slide 101
Stay in touch
Eat Shop Play has highlighted local businesses along the Purple Line Extension project in Koreatown, Miracle Mile, Beverly Hills, Century City, and Westwood, especially eateries and specialty businesses operating pick-up and delivery during the past months.
The Eat Shop Play program continues supporting local businesses as construction progresses by promoting them through regular social media posts and newsletters.

## Slide 102
Stay in touch
Kidsland
3700 Wilshire Bl # 125
​ Everything you need in baby supplies and strollers in Koreatown
Business hours:​ Mon-Fri: 11am-5pm
​
kidslandusa.com
866.462.7715

## Slide 103
Stay in touch
Pho Saigon Pearl
519 S Fairfax Av
​ Delicious, fresh, and authentic Vietnamese cuisine in Miracle Mile
Business hours​ Open Daily 12-9pm
phosaigonpearl.com
(323)930-8935
Notes: The Kohan family, proprietors of Wilshire Beauty, curates the most exclusive collection of American, European, and Japanese crèmes, lotions, mousses and applications found anywhere and bring the world’s finest beauty products under one roof.

## Slide 104
Stay in touch
Lazy Daisy
155 S Robertson Bl
​ Delicious homestyle breakfast, brunch, and lunch in Beverly Hills
Business hours​ Mon - Fri: 7am - 5pm
Sat - Sun: 7am - 4pm
​
lazydaisybeverlyhills.com
424.284.3387
Notes: The M Day Spa offers an extensive list of treatments ranging from massages, age reversal skin peels, lashes and brows, facials, face lifts, and more. Visit online for a full list of services and to book an appointment.

## Slide 105
Stay in touch
Craft Los Angeles
10100 Constellation Bl​
Seasonal farm-to-table New American food in Century City
Business hours​ Tue – Fri 11:30am -1:30pm, 5-9:30pm
Saturday: 5-9:30pm
​
www.craftlosangeles.com
310.279.4180

## Slide 106
Stay in touch
Toranj
10861 Lindbrook Dr​
Authentic Persian and Iranian food, stews, and kebabs in Westwood
Business hours​ Open Daily 11am-10pm
toranjrestaurant.com
310.824.8188
Notes: Meet yourself: In the light-free, sound-resistant, zero-gravity environment, the mind can redirect its thoughts and focus inward.
Perfect and unique Mother's Day gift. Book mom a session and literally give her 2 hours of peace and quiet to herself.

## Slide 107
Stay in touch
Contact Us
> For more information on Eat Shop Play visit​
metro.net/eatshopplay ​
> Send an email to eatshopplay@metro.net

## Slide 108
Business Interruption Fund (BIF)

## Slide 109: Metro’s Business Interruption Fund
BIF Information and Eligibility
Financial assistance to small “mom & pop” businesses with 25 or fewer full-time employees directly impacted by Metro Rail construction along three project areas​:
  Crenshaw/LAX Transit Project​
  Purple Line Extension, Sections 1, 2 & 3​
  Regional Connector Project, Little Tokyo area & 2nd/Broadway Segment*
Businesses must be located immediately adjacent to the rail corridor and meet other eligibility requirements​
Grant amounts are determined by business revenue loss directly related to period of Metro construction disruption​
Businesses may receive up to $50,000 per impact year
*Segment eligibility based on full street closure with duration greater than six continuous months. Eligibility ended 6/30/17.​

## Slide 110
Metro’s Business Interruption Fund
Metro’s Business Interruption Fund (BIF) is accepting applications for transit rail construction impact along the Crenshaw/LAX Transit Project, the Little Tokyo area of the Regional Connector and Sections 1, 2 and 3 of the Purple Line Extension sustained from March 20, 2020, forward (during the COVID-19 pandemic).
Small “mom and pop” businesses that experienced transit rail construction impact during the COVID-19 pandemic may be eligible.
Potentially eligible small business owners may contact BIF Fund Administrator Pacific Coast Regional at 213.739.2999 x223 or Metro at bif@metro.net.
Metro does not cover revenue loss nor fixed operating expenses related to COVID-19 impacts.

## Slide 111
Metro’s Business Interruption Fund
Chart: 
| Crenshaw/LAX Transit Project | Purple Line Extension Section 1 | Purple Line Extension Section 2 | Regional Connector, Little Tokyo Area | Regional Connector, 2nd/Broadway Segment
Total Grant Amount | 15090988.93 | 5485204.34 | 2111053.94 | 1996164.16 | 950164.03
  *BIF Grants do not cover COVID-19 related impacts.
Value of BIF Grants Awarded:
$35,358,152*

## Slide 112
Stay in Touch
213.922.6934
purplelineext@metro.net
metro.net/purple
@purplelineext
facebook.com/purplelineext