## Slide 1: We will get going in just a moment

## Slide 2: Thank you for joining us!

## Slide 3: Presentation Panelists
Metro Purple Line Extension Team
Marlon Walker, Community Relations Manager
  Sections 1, 2 & 3 and Division 20
Ned Racine, Principal Community Relations Officer
  Section 1 and Division 20
  Mindy Lake, Principal Community Relations Officer
  Section 1, Beverly Hills and Section 2
Metro Arts and Community Enrichment
Clare Haggarty, Senior Manager, Transportation Planning
Erik Qvale, Manager, Creative Services
Metro New Media Team​
Ginny Brideau, Manager, Community Relations New Media Team
Stephanie Molen, Principal Community Relations Officer New Media Team
Jesus Galeno, Community Relations New Media Team
Contractor Representatives and Presenters
Scott Donohue, STS Community Relations Coordinator
Matt Evans, TPOG Project Information Coordinator
Joanna Amador-Dempsy, Modern Times Community Relations Director
Metro Business Interruption Fund Team
Eric Chun, Sr. Transportation Planner (Interim)

## Slide 4: Today's Agenda
  2022 artist Pool for Digital Media Opportunities
  Project Overview
  Division 20 Section 1 Construction Update Section 2 Construction Update Section 3 Construction Update
  Eat Shop Play
  Business Interruption Fund

## Slide 5
2022 Artist Pool for Digital Media Opportunities
Please follow the link below for more details
metro.net/art under Art Opportunities.
Open to artists and artist teams working in digital media
Submittal deadline is August 31, 2022 at 11:59 pm

## Slide 6: Metro Art Bus .
#MetroArtBus #SomosWeAreLA.

## Slide 7
Purple Line Extension Alignment

## Slide 8
Sections 1, 2, & 3 Status
*Subject to change. The PLE project team is working to deliver the project consistent with Measure M.
 | Forecasted Schedule |  | 
Section | Section 1 | Section 2 | Section 3
Length | 3.92 Miles | 2.59 Miles | 2.56 Miles
New Stations | Wilshire/La Brea Wilshire/Fairfax Wilshire/La Cienega | Wilshire/Rodeo Century City/ Constellation | Westwood/UCLA Westwood/VA Hospital
Pre-Construction Activities | 2014 – 2015 | 2016 – 2018 | 2018 – 2019
Construction | 2015 – 2024 | 2018 – 2025 | 2019 – 2027
Operations | 2024 | 2025 | 2027

## Slide 10: Project Overview
  Operational improvements to Metro’s Division 20 Rail Yard will accommodate increased service levels on the Metro Red and Purple (B and D) Lines
  Improvements include:
    Widening of heavy rail portal
    New turnback facility
    Expansion and reconfiguration of rail storage tracks
Benefits
  Faster and more frequent service
Arts District Project Area
One Santa Fe
Tunnel Portal
Turnback Facility
Storage Tracks

## Slide 11: Current work- Portal Area
Before Construction
Bing Image
Current area*
*Delineations on the image are not to scale.

## Slide 13: Wilshire/La Brea Station Rendering

## Slide 14
Wilshire/La Brea Station Box
Outline of the Wilshire/La Brea underground station box on Wilshire Bl. from Orange Dr. to Detroit St.

## Slide 15: La Brea Station – Post Decking Restoration
Curb, Gutter, Bus Pad Restoration
Following deck removal, a work zone has been established on the north side of Wilshire Blvd. between Mansfield Ave. and La Brea Ave.
Work zone supports:
Curb and gutter restoration
Streetlight installation
Tree well installation
Wheelchair and bus lane
completion
Starting: July 2022
Duration: approximately 4 months
*Dates Subject to Change
Sycamore Restoration Orange Restoration
A traffic control plan for this phase of street restoration is being developed. More specific information will be available later this year.

## Slide 16: Work Behind the K-Rail
Sidewalk, curb, and gutter are demolished
in preparation for replacing the bus pad.

## Slide 17: Work Behind the K-Rail (Contd.)
Here workers will replace a temporary
storm drain with a permanent drain.

## Slide 18: Work Behind the K-Rail (Contd.)
Immediately south of the Avalon Apartments, workers prepare to replace the curb and gutter.

## Slide 19: Wilshire/Fairfax Station Rendering

## Slide 20
Fairfax Decking Removal - Sequence
Weekend | Dates
1 | September 9 – September 12
2 | September 16 – September 19
3 | September 23 – September 26
4 | September 30 – October 3
5 | October 7 – October 10
6 | October 14 – October 17
7 | October 21 – October 24
8 | October 28 – October 31
9 | November 4 – November 7
Veteran’s Day (No work) | November 11 – November 14
10 | November 18 – November 21
Thanksgiving (No work) | November 25 – November 28
11 | December 2 – December 5
12 | December 9 – December 12
13 | December 16 – December 19

## Slide 21: Fairfax Decking Removal – Phase 1
Weekend | Dates
1 | September 9 – September 12
2 | September 16 – September 19
3 | September 23 – September 26
4 | September 30 – October 3
5 | October 7 – October 10
6 | October 14 – October 17
7 | October 21 – October 24
Work will begin at 9pm on Friday night and continue through 6am on Monday morning. As a contingency, the design-builder has requested approval to extend work hours as late as 12 noon on Monday. The extension will only be used in the event of an emergency.
Decking Removal will begin at the Wilshire/Fairfax Station over the weekend of September 9 to September 12.
Phase 1, the area immediately east of Fairfax Av, will be the first section restored.
A full closure on Wilshire Bl will be in place over the duration of this work. Eastbound traffic will be detoured at Fairfax Av, and westbound traffic will be detoured at La Brea Av

## Slide 22: Fairfax Decking Removal – Phase 1 Detour Map
Eastbound Wilshire > Northbound Fairfax Av > Eastbound 6th St > Southbound La Brea Av > Eastbound Wilshire
Westbound Wilshire > Westbound 6th St > Southbound Fairfax Av > Westbound Wilshire

## Slide 23: Fairfax Decking Removal – Phase 2
Weekend | Dates
8 | October 28 – October 31
9 | November 4 – November 7
Work will begin at 9pm on Friday night and continue through 6am on Monday morning. As a contingency, the Design-Builder has requested approval to extend work hours as late as 12 noon on Monday. The extension will only be used in the event of an emergency.
Following Phase 1 Decking Removal, STS will begin working within the Wilshire/Fairfax Intersection.
This work will take two weekends to complete, October 28 – October 31, and November 4 to November 7
Full closures will be in place on Wilshire Bl and Fairfax Av. All traffic will be detoured around the workzone.
Southbound Fairfax Av traffic will be detoured at 6th St
Northbound Fairfax Av traffic will be detoured at Olympic Bl
Eastbound Wilshire Bl traffic will be detoured at La Cienega Bl and San Vicente Bl
Westbound Wilshire Bl traffic will be detoured at La Brea Av

## Slide 24: Fairfax Decking Removal – Phase 2 Detour Map
Eastbound Wilshire > Southbound La Cienega Bl> Westbound Olympic Bl > Northbound La Brea Av > Eastbound Wilshire
Eastbound Wilshire > Southbound San Vicente Bl > Northbound La Brea Av > Eastbound Wilshire
Westbound Wilshire > Southbound La Brea Av > Westbound Olympic Bl > Northbound San Vicente Bl > Westbound Wilshire
Northbound Fairfax Av > Eastbound Olympic Bl > Northbound La Brea Av > Westbound 6th St > Northbound Fairfax Av
Southbound Fairfax Av > Eastbound 6th St > Southbound La Brea Av > Westbound Olympic Bl > Southbound Fairfax Av

## Slide 25: Fairfax Decking Removal – Phase 3
Weekend | Dates
Veteran’s Day (No work) | November 11 – November 14
10 | November 18 – November 21
Thanksgiving (No work) | November 25 – November 28
11 | December 2 – December 5
12 | December 9 – December 12
13 | December 16 – December 19
Work will begin at 9pm on Friday night and continue through 6am on Monday morning. As a contingency, the Design-Builder has requested approval to extend work hours as late as 12 noon on Monday. The extension will only be used in the event of an emergency.
Following Phase 2 Removal, the third and final phase of work will begin to the west of Fairfax Av
This work will take place over 4 weekends, beginning on November 18.
Full closures will be in place at Fairfax Av and San Diego Way
Eastbound Wilshire will be detoured at La Cienega Bl or San Vicente Bl
Westbound Wilshire will be detoured at Fairfax Av

## Slide 26: Fairfax Decking Removal – Phase 3 Detour Map
Eastbound Wilshire > Southbound La Cienega Bl > Eastbound Olympic Bl > Northbound La Brea Av > Eastbound Wilshire
Eastbound Wilshire > Southbound San Vicente Bl > Northbound La Brea Av > Eastbound Wilshire
Westbound Wilshire > Southbound Fairfax Av > Northbound San Vicente Bl > Westbound Wilshire

## Slide 27: Fairfax Station – Decking Removal
Excavators and haul trucks will be utilized during backfilling operations.
Dozens of trucks will be used each weekend to haul steel, decking panels, and SOE out of the area.
Large cranes and other heavy equipment will lift the steel beams and deck panels out of the ground.

## Slide 28: Fairfax Station – Decking Removal
Following decking removal, steel beams and SOE haul out, and backfilling and utility placement, a new street surface will be placed from curb to curb.
Work will progress east to west, from one weekend to the next.

## Slide 29: La Brea Station – Decking Removal Equipment
Aboveground
Cranes
Haul trucks, dump trucks
Concrete pump
Loaders
Saw cutter, jackhammer
Vibrator, roller
Belowground
Compact excavators
Compact bulldozers
Man lifts, forklifts
Graders
Loaders

## Slide 30: Fairfax Station – Decking Removal Schedule
* Subject to Change
Decking removal will begin at 9pm on Friday and continue until Monday at 6am during 10 weekends between September 9, 2022 through December 19, 2022.

## Slide 31: Fairfax Station – Decking Removal Sequence (Part 1)
Activity | Occurs
Design-builder begins to remove deck panels along Wilshire Blvd. | Once road is closed to traffic (9pm)
Crews begin removing steel beams and support for excavation above the station | All day Saturday
Utilities will be relocated as needed. Trucks loaded with backfilling materials will be staged around the deck openings. | Saturday
Testing and quality assurance conclude prior to asphalt placement | All day Sunday

## Slide 32: Fairfax Station – Decking Removal Sequence (Part 2)
Activity | Occurs
Asphalt placement | Begins after backfilling (asphalt requires approximately four hours to cure/cool before it can carry weigh)
City agencies test asphalt to ensure that it will be safe for commuters | After curing
The final steps of decking removal includes striping, removing traffic control devices, and opening the road | Sunday night and Monday morning

## Slide 33: Outreach Schedule
Outreach | Occurs
STS and Metro discusses closures with Council District 5. | May 2022
Affected residents and business owners invited to online meetings to discuss decking removal. Meeting announcement appears on Weekly Look Ahead. | One month before work begins
Wilshire/Fairfax decking removal presented during quarterly webinar. | One month before work begins
Door-to-door outreach conducted. A Construction Notice will be widely distributed adjacent to the Wilshire/La Brea intersection. | One month before work begins
A Construction Notice will be re-issued on the Metro website and distributed to the Metro Email List. Computer message signs will be placed at the work area. | One week before work begins
A Construction Notice describing the work will be sent in the Weekly Look Ahead email. | Weekly

## Slide 34
Wilshire/La Cienega Station Rendering

## Slide 35
La Cienega Station Backfilling
*Subject to Approval
What: Beginning in August 2022, STS will begin Station Backfilling at La Cienega.
  This is the first of multiple construction activities in advance of decking removal and street restoration.
Why: The Station Roof is approximately 20ft below the street surface. That area will need to be filled with slurry, soil, and utilities.
  STS will need to restore utilities in the street, including sewer, storm drains, and other utilities.
Traffic Control and Work Hours: Additional information will be available in future construction notices and community presentations.
Backfilling operations at Wilshire Bl and Orange Dr, within the City of Los Angeles

## Slide 36
Wilshire/La Cienega Station Appendage Work
Why: Multiple appendages will be required for each station on the Purple Line Extension
Each appendage structure houses a vital function for the stations:
  Emergency exits
  Utility rooms
  Ventilation rooms
  Entrance and exit structures
When: Began in March 2021 through 2023*
Where: Information about specific traffic control and work hours will be available in future community meetings and construction notices
Coordination with impacted businesses will be conducted prior to the start of the next phase of appendage work

## Slide 37
Wilshire/La Cienega Station: Appendage Structures Phase 1A
Appendages – Northeast
Appendage – Main Entrance
Phase 1A
Phase 1A
Station Box
Station appendage locations

## Slide 38
Wilshire/La Cienega Station Appendage Work
*Dates subject to change.
Phase 1A Traffic Control (March 2021 through November 2022)*
Wilshire Blvd. between San Vicente Blvd. and La Cienega Blvd. reduced to two lanes in each direction.
Left turns from Wilshire Blvd. onto Gale Dr. will be restricted from both directions. Left turns from Tower Dr. onto westbound Wilshire Blvd. will be restricted.
The east/ west crosswalk on the south side of Wilshire Blvd. at Gale Dr. will be maintained.
The north sidewalk between San Vicente Blvd. and Gale Dr. will be closed during this phase of work. A pedestrian detour for east/west travel will be in place on the south side of Wilshire. Access to 8383 Wilshire will be maintained.
The loading zone in front of the Saban Theatre on Wilshire Blvd will be closed over the duration of this closure.
A full closure of Gale Dr. north of Wilshire Blvd. will be in place during Phase 1B of this work.

## Slide 39
Wilshire/La Cienega Station: Appendage Structures Phase 1B
*Dates subject to change.
Phase 1B
Phase 1B Traffic Control (January 7, 2022 through September 2022)*
Wilshire Blvd. between San Vicente Blvd. and La Cienega Blvd. reduced to two lanes in each direction
Gale Dr. north of Wilshire Blvd. will be fully closed through September 2022.
Left turns from Wilshire Blvd. onto Gale Dr. will be restricted.
Left turns from Tower Dr. onto Wilshire Blvd. will be restricted.
The north/south crosswalks at Gale Dr will be closed
The north sidewalk between San Vicente Blvd. and west of Gale Dr. will be closed during this phase of work. A pedestrian detour for east/west travel will be in place on the south side of Wilshire. Access to 8383 Wilshire will be maintained.
The loading zone in front of the Saban Theatre will be closed over the duration of this closure.
Station Box
Station appendage locations

## Slide 40
Wilshire/La Cienega Station Appendage Progress – Phase 1A

## Slide 41: Replacement Parking
Locations for One Hour Free Parking:
  8447 Wilshire Bl: Accessible from N Hamilton
  8350 Wilshire Bl: Accessible from S Tower
  Please mention "Metro" upon entering the building to receive the 1st hour free

## Slide 42
Concrete and Material Deliveries
Where: Structural work on the station underneath Wilshire Bl is generally conducted from the Gale Yard and from Wilshire Bl
Work Hours: 7am to 4pm. During bump out implementation: 9am-4pm
Traffic Controls*:
  Westbound Wilshire Bl will be intermittently reduced to one lane between San Vicente Bl and Hamilton Dr
  Daily closures will be utilized in support of ongoing work activities in the staging yard at Gale Dr
Deck Panel Access – Hamilton Dr (9am to 4pm, weekdays; 7am to 6pm, Saturdays)
  Beginning in April, intermittent deck panel access may be implemented within the Wilshire/Hamilton intersection.
  Wilshire will be reduced to a single lane in each direction between Tower Dr and Stanley Dr
  Left turns from Wilshire to Hamilton will be restricted. Through traffic on Hamilton will be restricted at Wilshire.
Outside Gale Staging Yard
Noise Mitigations: will remain in place
  Sound blankets around noisy equipment
  Trucks equipped with low-impact backup alarms
  Nylon straps used to lift material

## Slide 43
Next Steps: Station Construction
Construction of station roof will continue through 2022
Each roof placement will be 60 feet by 60 feet
Work activities in support of concrete and deliveries will be conducted within the staging yards, and occasionally on Wilshire Bl
Daily construction activities may be conducted underneath Wilshire Bl and from both Staging Yards for 24 hours a day
Illustration of station interior design

## Slide 44: La Cienega Station Progress
Looking East
Looking West

## Slide 45: La Cienega Station Progress
Looking East
Photo courtesy of Ken Karagozian

## Slide 46
Instrumentation Work
When: Ongoing in 2022
Traffic Controls:
  Intermittent lane reductions on Wilshire Bl, La Cienega Bl, and side streets during off-peak hours may be in place to support the maintenance of geotechnical instruments in the Wilshire Bl and La Cienega Bl area
  Intermittent lane reductions may be in place on Wilshire Bl, west of La Cienega Bl, to support coring survey work under Wilshire Bl
Additional details on this work will be available in future construction notices
Example of instrumentation drilling

## Slide 48
Wilshire/Rodeo Station Rendering

## Slide 49
Wilshire/Rodeo Station Box
Rendering shows length of the underground station box on Wilshire Bl from Cañon Dr to Beverly Dr

## Slide 50
Wilshire/Rodeo Station: Permitted Work Hours and Traffic Control
Work hours underneath the deck are 24 hours a day, 7 days a week. Deliveries of material, equipment, and concrete will be ongoing daily from Wilshire Bl. A breakdown of daily work hours on street level:
  From 7am to 9am and 4pm to 8:15pm, Wilshire Blvd. will remain open with three lanes in each direction between El Camino Dr. and Crescent Dr.
  From 9am to 4pm, Wilshire Blvd. may be reduced to two lanes in each direction between El Camino Dr. and Crescent Dr.
  From 8:15pm to 7am, Wilshire Blvd. may be reduced to one lane in each direction between El Camino Dr. and Crescent Dr.
Traffic control may also be implemented on Beverly Dr. At least one through traffic lane will be maintained in both directions between 9am-4pm and 8pm-7am.
From 9am to 4pm, S. Reeves Dr. may be reduced to one lane northbound. A flagger will be on site to assist motorists with 2-way traffic.

## Slide 51: Wilshire/Rodeo Station: Structure Construction through 2024

## Slide 52: Wilshire/Rodeo Tunneling Progress

## Slide 53: Wilshire/Rodeo Station: Concourse Level Activity
Concourse level shoring/initial pour progress

## Slide 54: Wilshire/Rodeo Station: Construction Progress
Entrance invert rebar installation progress.

## Slide 55: Wilshire/Rodeo Station: Construction Progress
Entrance Wall progress.

## Slide 56
Upcoming SCE Installation Work
Where: Wilshire Blvd. between Dayton Way and Rexford Dr.
Duration: ~ 7 months [Anticipated start in August/September]
Work Hours: Weekdays, 9am to 4pm and 8pm-7am
Traffic Control:
  Wilshire Blvd. may be reduced to two lanes in each direction during the day and one lane overnight
Contractor will begin installation of SCE Permanent Power Feeds to the station.
*Pending approval from City Of Beverly Hills

## Slide 57
Upcoming Ground Improvement/Cross Passage Work
The contractor began ground improvement work along the tunnel alignment in preparation for the construction of cross passage tunnels.
When: Work started in late May
  Ongoing until late 2022
Where: *14 locations; First 7 work sites noted on map
Work Hours: Monday-Friday 8am-6pm off Wilshire and 8am-11pm on Wilshire: Closures remain in place 24/7 until each location is completed
Duration: 2-4 weeks/location
*Additional notices detailing dates & closure information will be provided in advance

## Slide 58
Upcoming Ground Improvement/Cross Passage Work
*Additional notices detailing dates & closure information will be provided in advance

## Slide 59
Wilshire/Rodeo Station: Geotechnical Instrumentation
Where: Instruments will be installed within the tunnel alignment and station box area to monitor ground movement, settlement and other geological conditions
  Installations will be within the public right of way and within privately owned properties
Duration: Ongoing
Work Hours On Wilshire Bl:
  Weekdays, 7am to 4pm and 8pm to 7am
Work Hours Off Wilshire Bl:
  Weekdays, 8am to 6pm and 8pm to 7am
Example of 10-foot geotechnical instrumentation pole.

## Slide 60: Tunnel Boring Machine (TBM) Update
Tunneling Statistics As of (8/3/2022) | 
Ruth | 11,510 feet (total journey) 80% complete
Harriet | 11,510 feet (total journey) 85% complete
Both TBM’s have passed through the Wilshire/Rodeo Station
Will continue mining east towards Wilshire/La Cienega
Tunneling Duration: Approximately 2 years from the start
Remaining Duration: 2-4 months

## Slide 61
Wilshire/Rodeo Request for Holiday Moratorium Exemption
Metro and the contractor has submitted an application to the City of Beverly Hills requesting a waiver of the 2022 Holiday Moratorium, which would allow work to continue after the Thanksgiving Holiday through New Year’s Eve.
  No work is planned for Thanksgiving Day, the day after Thanksgiving Day, the first night of Hanukkah, Christmas Eve, Christmas Day, New Year's Eve or New Year’s Day.

## Slide 62: Century City/Constellation Station Rendering

## Slide 63: Century City/Constellation: Station Box
Length of the underground station box on Constellation Blvd.
from Century Park East to Avenue of the Stars.

## Slide 64: Century City/Constellation: Station Excavation
Excavation of the underground station underneath Constellation Blvd. is in progress and will continue until reaching approximately 100 feet in depth.
  70’ east of Avenue of the Stars
  30’ west of Avenue of the Stars
Work Hours: 24 hours a day, 5 days a week (Monday – Friday)
Anticipated Completion: 1st quarter 2023
Temporary partial traffic lane closures may be required on Constellation Blvd. both east and west of Avenue of the Stars to facilitate this work.
Looking west at AOS/Constellation intersection; station entrance to the right

## Slide 65: Station Entrance Excavation

## Slide 66: Sanitary Sewer and Storm Drain Relocation
Ongoing: (Work started in March 2022)
Anticipated Duration: Through end of January 2023
Anticipated Traffic Control*:
  Lane closures on Avenue of the Stars
  Night closures (8pm to 6am) will be required intermittently

## Slide 67: Stage 8 (Current Steady State Closures)
Anticipated Duration: 5-6 months
Work Hours: 24 hours a day, 7 days a week
What to Expect: Potholing, piling, shoring, and utility installation
Work Area
Work Area
Driveway open
Driveway open
Driveway open
Delivery driveway open
Intermittent closure
Traffic Control:
  No left turns on NB AOS onto WB Constellation Bl
  Intermittent closure of access lane on south side of Constellation Bl.

## Slide 68: Stage 8.1
Anticipated Duration: Intermittently during Stage 8
Work Hours: 8pm to 6am
What to Expect: Potholing, piling, shoring, and utility installation
Driveway open
Driveway open
Driveway open
Delivery driveway open
Intermittent closure
Traffic Control:
  No left turns on SB AOS onto EB Constellation Bl | Right turn restricted on SB AOS at Constellation Bl.
  Intermittent closure of access lane on south side of Constellation Bl.
Night-time additional closure

## Slide 69: Stage 7B (Steady State Closure)
Anticipated Duration:
  2 years (Re-implemented after utility relocation)
Traffic Control:
  One eastbound and westbound lane are accessible from CPW to AOS
  Maintaining access to Westfield driveways and Fairmont Century Plaza Hotel
Driveway open
Driveway open
Driveway open
Delivery driveway open

## Slide 71
Section 3 Tunnel From Century City to Westwood

## Slide 72
Section 3 Tunneling Progress
Aura (TBM 2)
Iris (TBM 1)
7,463 feet
55% complete
8,639 feet
64% complete
Tunneling Statistics
as of 7/31/2022
Future Station Boxes

## Slide 73
Westwood/UCLA Station Rendering (Northwest Entrance)

## Slide 74
Westwood/UCLA Station Rendering (Northeast Entrance)

## Slide 75: Westwood/UCLA Station Rendering (Southeast Entrance)
DRAFT

## Slide 76
Westwood/UCLA Station Box
Rendering shows length of the underground station box on Wilshire Bl between Westwood Bl and Veteran Av.
Construction continues in UCLA Lot 36. Some work may overlap onto the sidewalk.

## Slide 77
Piling Progress Westwood/UCLA Station

## Slide 78: Westwood/UCLA Station Piling
428 Piles Installed. 468 Total Piles for Station.

## Slide 79: Westwood/UCLA Piling Stage 2F- August 11
Nightly:
Mon- Fri, 9pm to 6am
Weekends:
Continuous, 9pm, Fri to 6am, Mon
*Construction is dynamic and subject to change​.​
Restoration and traffic control switch in preparation of Decking to occur on a continuous weekend, Friday, August 12 through Monday, August 15, 2022, from 11 pm to 6am. This will require lane closures. One lane of traffic maintained in each direction.

## Slide 80: Decking
Decking is a process where the street is excavated from curb to curb at a depth of about 10 to 12 feet. The deck beams are installed over the piles that have been installed. The concrete precast panels are place over the piles and create a temporary street surface. The panels get restriped for vehicular and pedestrian use.
Temporary partial street closures will be implemented on Wilshire Bl. Traffic will be detoured around the construction work.
Closures will occur on continuous weekends, Friday to Monday, 11 pm to 6am.
Decking anticipated for 14 continuous weekends beginning Mid- August.

## Slide 81: Decking Traffic Control
Tentative to start the weekend August 19 to continue for 13 consecutive weekends. No work on the labor day weekend.
Eastbound Wilshire Bl traffic access maintained with two lanes of traffic.
Westbound Wilshire Bl traffic detoured at Westwood either to Kinross Av or Ohio Av.
Northbound and Southbound traffic maintained through Stage 1 for Westwood Bl, Veteran Av, and Gayley Av.
*Traffic control plans pending approval

## Slide 82: Example of Decking on Bonsall Av.

## Slide 83: Holiday Moratorium Exemption
The holiday moratorium applies typically from November 25 through January 1. An exemption allows for a continuance with construction activities during the holiday season. TPOG will be requesting exemptions to allow construction to continue for both stations this year.
Coordination will occur with Council District 5, Council District 11, Bureau of Engineering (BOE) and the LA Department of Transportation (LADOT).
Continued work will ensure the construction schedule is maintained.
No work on Thanksgiving Day (November 24), Christmas Day (December 25) and New Year's Day (January 1st).

## Slide 84: Westwood/VA Hospital Station Rendering

## Slide 85
Westwood/VA Hospital Station Rendering (Bonsall Av)

## Slide 86
Westwood/VA Hospital Station Box

## Slide 87
Instrumentation Installation: SB 405 Ramp Closures
Instrumentation installation around the VA Station is starting and will continue with more activity in August.
The SB 405 On-Ramp will be closed from 11pm to 6am, August 3 to August 10, 2022.
The SB 405 Off-Ramp will be closed from 9pm to 5am, August 10 to August 12, 2022.
The WB 405 On-Ramp will be closed from 1am to 6am, August 12 to August 18, 2022.
*Construction is dynamic and subject to change​.​

## Slide 88
Westwood/VA Hospital Upcoming Waterline Work
Wilshire Blvd
Federal Ave
Traffic Control:
VA Hospital access will be detoured nightly along Sepulveda Bl and Santa Monica Bl to Sawtelle Bl and Dowlen Dr.
Where: Wilshire Bl, Federal Av, and Bonsall Av
When: Fall of 2022*
Work Hours: Vary depending on the work scheduled in each stage.
Monday to Friday, 9am to 3:30pm, 7pm to 6am, Monday to Sunday, and 11pm to 6am, Monday to Sunday.
*Construction is dynamic and subject to change​.​
Click to add text

## Slide 89
Piece by Piece

## Slide 90: VA Mural Project History
1995: Artist and U.S. Navy veteran, Peter Stewart, with donated art materials and volunteers envisioned and created a tribute mural near the VA Greater Los Angeles Healthcare Center in Westwood. The specific area eventually selected was the underpass at the intersection of Bonsall Ave and Wilshire Blvd, north of the West LA VA Medical Center Campus.
Stewart died before the mural was fully completed. The mural remained unfinished, but it has become a treasured and honored landmark for veterans and VA staff.
2012: Metro’s Purple Line Extension Final EIR/EIS in 2012 assumes that the mural could be protected in place during construction. However, subsequent studies show that removal of the northeast mural is necessary to build key Westwood/VA Medical station design elements. Attempting to rescue the mural is deemed unfeasible due to existing wall conditions.

## Slide 91: VA Murals to Remain in Place

## Slide 92: VA Legacy Art Mural
Project planners found that there is not sufficient space to accommodate the mural in its original location.
Therefore, plans were developed to decommission approximately 115 feet of the 23,000 square foot mural during the construction of the north entrance to the Westwood/VA Metro Station.
Only portion of mural to be removed is located at the westbound Wilshire Blvd off-ramp to Bonsall Ave.
Impacted Section of the Mural

## Slide 93: VA Legacy Art Mural

## Slide 94
Shad Meshad, founder, National Veterans Foundation

## Slide 95: Engaging the Veteran Community
To honor this section of the mural, Metro will engage the services of an arts organization to work with the veteran community on a Veterans Legacy Art Project.
Veterans will participate throughout the design process that will lead to a mosaic mural to be installed across the street from the original.
Final design will be determined with veteran involvement and input.
Outreach and Engagement scheduled for 2024.
Removal of mural wall scheduled for 2025.

## Slide 96
Stay in touch
Eat Shop Play has highlighted local businesses along the Purple Line Extension project in Koreatown, Miracle Mile, Beverly Hills, Century City, and Westwood, especially eateries and specialty businesses operating pick-up and delivery during the past months.
The Eat Shop Play program continues supporting local businesses as construction progresses by promoting them through regular social media posts and newsletters.

## Slide 97
Stay in touch
Kidsland
3700 Wilshire Bl # 125
​ Everything you need in baby supplies and strollers in Koreatown
Business hours:​ Mon-Fri: 11am-5pm
​
kidslandusa.com
866.462.7715

## Slide 98
Stay in touch
Pho Saigon Pearl
519 S Fairfax Av
​ Delicious, fresh, and authentic Vietnamese cuisine in Miracle Mile
Business hours​ Open Daily 12-9pm
phosaigonpearl.com
(323)930-8935
Notes: The Kohan family, proprietors of Wilshire Beauty, curates the most exclusive collection of American, European, and Japanese crèmes, lotions, mousses and applications found anywhere and bring the world’s finest beauty products under one roof.

## Slide 99
Stay in touch
Lazy Daisy
155 S Robertson Bl
​ Delicious homestyle breakfast, brunch, and lunch in Beverly Hills
Business hours​ Mon - Fri: 7am - 5pm
Sat - Sun: 7am - 4pm
​
lazydaisybeverlyhills.com
424.284.3387
Notes: The M Day Spa offers an extensive list of treatments ranging from massages, age reversal skin peels, lashes and brows, facials, face lifts, and more. Visit online for a full list of services and to book an appointment.

## Slide 100
Stay in touch
Craft Los Angeles
10100 Constellation Bl​
Seasonal farm-to-table New American food in Century City
Business hours​ Tue – Fri 11:30am -1:30pm, 5-9:30pm
Saturday: 5-9:30pm
​
www.craftlosangeles.com
310.279.4180

## Slide 101
Stay in touch
Toranj
10861 Lindbrook Dr​
Authentic Persian and Iranian food, stews, and kebabs in Westwood
Business hours​ Open Daily 11am-10pm
toranjrestaurant.com
310.824.8188
Notes: Meet yourself: In the light-free, sound-resistant, zero-gravity environment, the mind can redirect its thoughts and focus inward.
Perfect and unique Mother's Day gift. Book mom a session and literally give her 2 hours of peace and quiet to herself.

## Slide 102
Stay in touch
Contact Us
> For more information on Eat Shop Play visit​
metro.net/eatshopplay ​
> Send an email to eatshopplay@metro.net

## Slide 103
Business Interruption Fund (BIF)

## Slide 104: Metro’s Business Interruption Fund
BIF Information and Eligibility
Financial assistance to small “mom & pop” businesses with 25 or fewer full-time employees directly impacted by Metro Rail construction along three project areas​:
  Crenshaw/LAX Transit Project​
  Purple Line Extension, Sections 1, 2 & 3​
  Regional Connector Project, Little Tokyo area & 2nd/Broadway Segment*
Businesses must be located immediately adjacent to the rail corridor and meet other eligibility requirements​
Grant amounts are determined by business revenue loss directly related to period of Metro construction disruption​
Businesses may receive up to $50,000 per impact year
*Segment eligibility based on full street closure with duration greater than six continuous months. Eligibility ended 6/30/17.​

## Slide 105
Metro’s Business Interruption Fund
Metro’s Business Interruption Fund (BIF) is accepting applications for transit rail construction impact along the Crenshaw/LAX Transit Project, the Little Tokyo area of the Regional Connector and Sections 1, 2 and 3 of the Purple Line Extension sustained from March 20, 2020, forward (during the COVID-19 pandemic).
Small “mom and pop” businesses that experienced transit rail construction impact during the COVID-19 pandemic may be eligible.
Potentially eligible small business owners may contact BIF Fund Administrator Pacific Coast Regional at 213.739.2999 x223 or Metro at bif@metro.net.
Metro does not cover revenue loss nor fixed operating expenses related to COVID-19 impacts.

## Slide 106
Metro’s Business Interruption Fund
Chart: 
| Crenshaw/LAX Transit Project | Purple Line Extension Section 1 | Purple Line Extension Section 2 | Regional Connector, Little Tokyo Area | Regional Connector, 2nd/Broadway Segment
Total Grant Amount | 15090988.93 | 5485204.34 | 2111053.94 | 1996164.16 | 950164.03
  *BIF Grants do not cover COVID-19 related impacts.
Value of BIF Grants Awarded:
$34,643,968.17*

## Slide 107
Stay in Touch
Upcoming Meeting Dates
PLE Sections 1 & 2 La Cienega and Rodeo Stations Construction In-person Meeting will be held on
September 7, 2022 at 6:00 PM at Beverly Hills City Hall 455 N Rexford Dr, Beverly Hills, CA 90210
Save the Date: Next PLE 123 Meeting
November 2, 2022 at 12 Noon Via Zoom
at https://zoom.us/j/96626476708 . If unable to use a smartphone, please call 669.900.9128, and enter the webinar ID: 966 2647 6708
213.922.6934
purplelineext@metro.net
metro.net/purple
@purplelineext
facebook.com/purplelineext