## Slide 2: We will begin soon

## Slide 3: Panelist
Metro Purple (D) Line Extension Team
  Marlon Walker, Community Relations Manager
  Glyssa Robles, Principal Community Relations Officer
Metro New Media Team
  Stephanie Molen, Principal Community Relations Officer
Contractor Team
  Joanna Amador-Dempsey, Public Information Coordinator

## Slide 4
Purple Line Extension Alignment

## Slide 5
Sections 1, 2, & 3 Status
*Subject to change. The PLE project team is working to deliver the project consistent with Measure M.
 | Forecasted Schedule |  | 
Section | Section 1 | Section 2 | Section 3
Length | 3.92 Miles | 2.59 Miles | 2.56 Miles
New Stations | Wilshire/La Brea Wilshire/Fairfax Wilshire/La Cienega | Wilshire/Rodeo Century City/ Constellation | Westwood/UCLA Westwood/VA Hospital
Pre-Construction Activities | 2014 – 2015 | 2016 – 2018 | 2018 – 2019
Construction | 2015 – 2024 | 2018 – 2025 | 2019 – 2027
Operations | 2024 | 2025 | 2027

## Slide 6: Section 3 Tunnel From Century City to Westwood

## Slide 7
Westwood/UCLA Station Rendering (Northwest Entrance)

## Slide 8
Westwood/UCLA Station Rendering (Northeast Entrance)

## Slide 9: Westwood/UCLA Station Rendering (Southeast)
DRAFT

## Slide 10: Westwood/UCLA Station Box
Rendering shows length of the underground station box on Wilshire Bl between Westwood Bl and Veteran Av

## Slide 11
Piling for the Westwood/UCLA Station

## Slide 12
Piling for the Westwood/UCLA Station

## Slide 13: Westwood/UCLA Station Piling
311 Piles Installed. 468 Total Piles for Station.

## Slide 14
Piling Progress Westwood/UCLA Station

## Slide 15: Westwood/UCLA Piling Stage 2
Nightly:
Mon to Thurs, 9pm to 6am
Weekend:
Continuous 9pm, Fri to 6am, Mon

## Slide 16: Stage 2F: May 20 through the end of June
Nightly:
Mon to Thurs, 9pm to 6am
Weekend:
Continuous 9pm, Fri to 6am, Mon

## Slide 17: Decking for the Westwood/UCLA Station
Anticipated Summer 2022*
Deck installation will be on Wilshire Bl between Westwood Bl and Veteran Av.
Construction of a concrete deck, curb to curb, approximately 12 ft deep.
Decking will serve as temporary street surface.
*Construction is a dynamic process. The schedule is subject to change

## Slide 18: Decking for the Westwood/UCLA Station
Traffic will travel on the deck panels while the station is constructed underground.
Temporary partial street closures will be implemented on Wilshire Bl. Traffic will be detoured around the construction work.
Station Box is 894 ft long, 75 ft wide, 65 ft deep.
Over 700 panels will be installed during decking.
*Construction is a dynamic process. The schedule is subject to change

## Slide 19: Decking for the Westwood/UCLA Station
Duration:
There are 4 stages for decking with varying traffic patterns.
Anticipated for 14 weekends to complete
Typical Work Schedule:
Work will be completed on weekend, Friday to Monday, 11 pm to 6am
Work Activities:
Excavation to uncover cap beam and piles
Install deck beam supporting the deck panels
Restriping the deck panels for future community use
*Construction is dynamic and the schedule is subject to change​

## Slide 20: Decking for the Westwood/UCLA Station

## Slide 21
Examples of Decking on Bonsall Av at the VA Hospital Campus

## Slide 22
Decking: Stage 1
The red is the work area and yellow is the closure.
Eastbound Wilshire Bl traffic access maintained.
Westbound traffic detoured at Westwood Bl either to Kinross Av or Ohio Av.
*Construction is dynamic and the schedule is subject to change​. Plans are pending approval.

## Slide 23: Decking: Stage 2 West
The red is the work area and yellow is the closure.​
Eastbound Wilshire Bl traffic access maintained.​
SB/NB Gayley Av thru traffic restricted.
Westbound traffic detoured at Westwood either to Kinross Av or Ohio Av.
*Construction is dynamic and the schedule is subject to change​. Plans are pending approval.

## Slide 24: Decking: Stage 2 East
The red is the work area and yellow is the closure.​
Eastbound Wilshire Bl traffic access maintained.​
SB/NB Gayley Av thru traffic restricted.
Westbound traffic detoured at Westwood either to Kinross Av or Ohio Av.
*Construction is dynamic and the schedule is subject to change​. Plans are pending approval.

## Slide 25: Decking: Stage 3
The red is the work area and yellow is the closure.
Eastbound Wilshire Bl traffic access maintained.
Westbound traffic detoured at Westwood Bl either to Kinross Av or Ohio Av.
*Construction is dynamic and the schedule is subject to change​. Plans are pending approval.

## Slide 26: Decking: Stage 4
The red is the work area and yellow is the closure.
Eastbound Wilshire Bl traffic access maintained.
SB Westwood Bl closed to thru traffic.
Westbound traffic detoured at Westwood either to Kinross Av or Ohio Av.
*Construction is dynamic and the schedule is subject to change​. Plans are pending approval.

## Slide 27
Examples of Decking on Bonsall Av at the West LA VA Campus

## Slide 28
Temporary Bus Stops Relocation

## Slide 29: Community Outreach
Community Meetings
Quarterly Webinars
Monthly Westwood Building Managers Meetings
Hand delivered construction notices
Email construction notices and updates
Paid media: radio, print, social media ads, UCLA kiosks

## Slide 30: Construction Mitigation
Traffic enforcement by LAPD
Traffic control officers from LADOT
Coordinated adjusted signal timing
Pedestrian access is maintained
Crosswalk detours around active construction areas
Education and outreach to adjacent properties
Coordination with other developers and nearby projects

## Slide 31: Construction Mitigation Banners

## Slide 32: Construction Mitigation Banners

## Slide 33
Stay in Touch
Lunch with Us Webinar: Sections 1, 2, and 3 Construction Update August 3, 2022
12pm to 1pm
Link to webinars available at metro.net/purple
213.922.6934
purplelineext@metro.net
metro.net/purple
@purplelineext
facebook.com/purplelineext